## Checklist
Check ID | Section | Check | How to Verify | Pass Criteria | Result | Notes
CK-01 | 1 — Swatch Display | Colour swatches are displayed below the product tile on PLP | 1. Navigate to acceptance.net-a-porter.com/en-de or acceptance.mrporter.com/en-de. 2. Open a category or search results page. 3. Locate a product with multiple colour variants. 4. Observe the area below the product image tile. | Swatches visible below product tile for colour-linked products. |  | Maps to G2-19278_TC01 ¦ G2-18440 AC1
CK-02 | 2 — Swatch Interaction | Clicking a swatch swaps the main product image, updates URL and highlights the selected swatch | 1. Find a product with multiple swatches on PLP. 2. Note the initial product image and page URL. 3. Click a swatch different from the default colour. 4. Observe image, URL and swatch visual state. | Image swaps to selected colour; URL updates to new slug; clicked swatch visually highlighted. |  | Maps to G2-19278_TC02 ¦ G2-18440 AC2
CK-03 | 3 — Overflow Colours | Maximum 4 swatches shown; (+) indicator present for products with 5+ colour variants | 1. Find a product with 5 or more colour variants. 2. Count swatches displayed below the tile. 3. Check for a (+) overflow indicator. | Exactly 4 swatches displayed; (+) visible for products with more than 4 colours. |  | Maps to G2-19278_TC03 ¦ G2-18440 AC3
CK-04 | 3 — Overflow Colours | Hovering over (+) restores the cover/main product image | 1. Click a non-default swatch to change the tile image. 2. Move cursor to hover over the (+) indicator. 3. Observe the product tile image. | Cover/main product image restored on (+) hover; no navigation triggered. |  | Maps to G2-19278_TC04 ¦ G2-18440 AC4
CK-05 | 3 — Overflow Colours | Clicking (+) navigates to the cover/default colour PDP | 1. On a tile showing (+), click the (+) indicator. 2. Observe the resulting page and URL. | Browser navigates to the PDP of the cover/default colour variant. |  | Maps to G2-19278_TC05 ¦ G2-18440 AC5
CK-06 | 4 — Stock Visibility | Out of stock colour variants remain visible as swatches on PLP | 1. Identify a product with at least one OOS colour variant (coordinate with trading/QA for test data). 2. Navigate to a PLP listing that product. 3. Observe the swatch row below the tile. | OOS colour swatch visible below tile; not suppressed. |  | Maps to G2-19278_TC06 ¦ G2-18440 AC6 ¦ Note: GAP-02 — no explicit OOS visual spec
CK-07 | 5 — Deep Linking | Each swatch click navigates to that colour's correct PDP URL | 1. On a multi-colour product tile, click each swatch in turn. 2. Check or copy the resulting URL after each click. 3. Verify each URL matches the expected slug for that colour variant. | Every swatch resolves to its correct colour-specific PDP URL. |  | Maps to G2-19278_TC07 ¦ G2-18440 AC7
CK-08 | 6 — Dual Brand Coverage | Colour swatches feature functional on both NAP and MRP | 1. Repeat CK-01 to CK-07 on acceptance.net-a-porter.com/en-de. 2. Repeat CK-01 to CK-07 on acceptance.mrporter.com/en-de. | All swatch checks pass on both NAP and MRP. |  | Maps to G2-19278_TC08 ¦ Epic AC Scope

## Overview
Field | Value
Plan | G2-19278 UAT — PLP ¦ Colour Linking
Generated | 2026-07-30
Epic | G2-19278 — PLP ¦ Colour linking
Epic Status | Done
Epic created by | Kozlova, Nika ¦¦ External (nika.kozlova.external@mytheresa.com)
Component | D1 — NAP/MRP - Search & Browse
Application URL — NAP | https://acceptance.net-a-porter.com/en-de
Application URL — MRP | https://acceptance.mrporter.com/en-de
Audience | Business quick-check
Timebox | ~60 minutes
Coverage | 8 AC-driven checks (CK-01–CK-08) + 3 Exploratory/Design Observations
Stories in scope | G2-18440 — FE: PLP ¦ Colour swatches (fully UI-testable) G2-18439 — BE: PLP API ¦ Colour linking (mixed; BE pipeline items excluded, observable outcome covered by checks)
Stories excluded (non-UI-testable) | G2-17553 — BE: Tapir ¦ Indexing ¦ Export colour linking data to Mink — pure backend data transfer, no observable UI outcome
Out of scope | PIM Data Ingestion (Discover3); Akamai/Madame swatch image flow; Sold-out swatch visual treatment on PLP (addressed separately)
Dev Evidence | G2-18440: Available — PR #429 [G2-18440] PLP color swatches in atelier, MERGED 2026-03-12 G2-18439: Available — PRs #2417 #2419 in hyena + PRs #45 #46 #47 #48 #49 in mink, all MERGED G2-19278 (Epic): Evidence Unavailable — no PRs/commits returned at Epic level
Gaps | GAP-01: Epic-level GitHub dev info returns no PRs (evidence attributed to story-level PRs) GAP-02: No explicit OOS visual spec on PLP; 'Sold out visibility — TBC' per G2-18440 Notes GAP-03: Test Scenarios in G2-18439 and G2-17553 both marked TBC; plan relies entirely on AC text GAP-04: Bug G2-20786 referenced in G2-18440 comment; resolution status unverified — confirm before UAT

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability / Requirement | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type
G2-19278_TC01 | G2-18440 | AC1 | Colour swatches displayed below product tile on PLP | High | CK-01 | Exact | PR #429 [G2-18440] PLP color swatches — atelier — MERGED 2026-03-12 | Available | AC
G2-19278_TC02 | G2-18440 | AC2 | Selecting a swatch swaps main product image, updates PLP URL and visually highlights selected swatch | High | CK-02 | Exact | PR #429 [G2-18440] PLP color swatches — atelier — MERGED 2026-03-12 | Available | AC
G2-19278_TC03 | G2-18440 | AC3 | Maximum 4 swatches shown on tile; (+) indicator displayed when more colours exist | High | CK-03 | Exact | PR #429 [G2-18440] PLP color swatches — atelier — MERGED 2026-03-12 | Available | AC
G2-19278_TC04 | G2-18440 | AC4 | Hovering over (+) restores the cover / main product image | Medium | CK-04 | Exact | PR #429 [G2-18440] PLP color swatches — atelier — MERGED 2026-03-12 | Available | AC
G2-19278_TC05 | G2-18440 | AC5 | Clicking (+) navigates user to the cover / default colour PDP | Medium | CK-05 | Exact | PR #429 [G2-18440] PLP color swatches — atelier — MERGED 2026-03-12 | Available | AC
G2-19278_TC06 | G2-18440 | AC6 | Out of stock colour variants remain visible as swatches on PLP (no suppression) | Medium | CK-06 | Exact | PR #429 — atelier MERGED; bug G2-20786 noted in comments (verify resolution before UAT) | Available | AC
G2-19278_TC07 | G2-18440 | AC7 | Deep link: each swatch click navigates to that colour's correct PDP URL | High | CK-07 | Exact | PR #429 [G2-18440] PLP color swatches — atelier — MERGED 2026-03-12 | Available | AC
G2-19278_TC08 | G2-19278 (Epic) / G2-18440 | Epic AC1 + Scope | Colour swatches feature fully functional on both NAP and MRP brands | High | CK-08 | Exact | Epic AC states both NAP and MRP; G2-18440 explicitly scoped to both brands; Epic-level GitHub: Evidence Unavailable | Evidence Unavailable (Epic-level GitHub) | AC

## Exploratory and Design Obs
Observation ID | Source Type | Jira Source | Observation Summary | How to Validate Manually | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes | Status
OBS-01 | Comment | G2-18440 (comment 738669) | Bug G2-20786 raised for some products' colour swatches; resolution status unknown at plan generation time | Identify products affected by G2-20786; check swatch display and interaction for correctness | Swatch display and interaction consistent across all products; no broken or missing swatches | Medium — could affect conversion on specific SKUs | G2-19278_TC01, G2-19278_TC02 | G2-20786 referenced by ext.pjassu in G2-18440 comment 738669; verify status before UAT sign-off | OBSERVE
OBS-02 | Story Note | G2-18439 (comment 734636) | A product should NOT appear in its own alternativeColors list; backend changed to exclude self-references | On PLP, verify swatches do not include the cover colour as a duplicate; cover is either the active default or absent from the overflow row | No duplicate self-reference swatch; swatch count accurate to actual colour variant count | Low — data quality; affects user perception of colour count | G2-19278_TC03 | Confirmed by ext.pjassu comment on G2-18439; PRs #2417 #2419 in hyena MERGED with this fix | OBSERVE
OBS-03 | Design | G2-18440 (description) | Figma designs provided for NAP and MRP; swatch layout and style should match brand designs | Compare rendered swatches on acceptance against Figma — NAP: https://www.figma.com/design/AClD0sJnAeZlWbchDF8JHm ¦ MRP: https://www.figma.com/design/UDgQqNHggMzHOTqaBaZ37a — check swatch size, spacing, highlight style and (+) indicator per brand | Swatch size, spacing, highlight style and (+) overflow indicator align with Figma designs for each brand | Medium — visual inconsistency may reduce brand confidence | G2-19278_TC01, G2-19278_TC08 | Figma links explicitly in G2-18440 description; screenshot of expected layout embedded in story | OBSERVE