## Overview
G2-16314 UAT - Migrate Registered User Data
Epic Key | G2-16314
Epic Slug | migrate-registered-user-data-from-wcs-to-tapir
Generated Date | 2026-08-05
Epic Summary | Migrate registered user data from WCS to Tapir
Epic Status | Done
Created By | Cobbe, Valentina ¦¦ YOOX NET A PORTER
Component | CD1
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 35-45 minutes
Coverage Summary | [Reduced V2 ~22% — 7/9 checks retained; AC coverage guardrail enforced] 4 UI-testable migration stories mapped to 9 business checks and 7 coverage rows. 9 non-UI stories and spikes are excluded from direct business execution.
Stories In Scope | G2-16757 ¦ Migration of registered user profile data from legacy ¦ Done G2-18353 ¦ Ant moves addresses to Tapir for bulk migration ¦ Done G2-18354 ¦ Tapir bulk migration of addresses ¦ Done G2-21527 ¦ Map WCS passwordHashed property correctly ¦ Done
Stories Excluded | G2-16688 ¦ Evaluation spike for cleansing-tool feasibility; no direct business UI acceptance path G2-17614 ¦ Infrastructure/mapping spike; analysis-only outcome G2-17629 ¦ Infrastructure provisioning task, not business-user executable G2-17674 ¦ Ant splitter/mapper job internals, backend processing only G2-18316 ¦ Monitoring dashboard wiring only G2-18352 ¦ Queue monitoring and reporting tooling only G2-19083 ¦ Tapir internal refactor and endpoint isolation hardening G2-19100 ¦ Integration mode configuration (HTTP/QUEUE), technical setup G2-20057 ¦ ParentURN mapping refactor technical follow-up
Out of Scope | Backend implementation internals, queue metrics deep-dive, load/performance profiling, and direct DB table verification outside business-user UAT scope.
Dev Evidence | GitHub key lookups were executed for all 4 in-scope stories and returned no direct PR matches. Jira-link fallback scans on description/comments/issuelinks/remotelinks also returned no PR or commit URLs. Status: Evidence Unavailable for G2-16757, G2-18353, G2-18354, G2-21527.
Gaps Summary | Story-level AC is mostly technical and does not define storefront UI steps explicitly; checklist is derived from business outcomes (account continuity, address continuity, login continuity). No linked PR/commit URLs were discoverable via GitHub MCP or Jira fallback. Password hash encoder variants (bcrypt vs argon2i) are noted in Jira comments and should be explicitly smoke-tested with representative migrated users.
Token Telemetry | payload_bytes=11582; payload_chars=11580; est_tokens~2895; checklist_rows=7; matrix_rows=7; exploratory_rows=3
Output Path | uat-test-plans-reduced30/G2-16314-migrate-registered-user-data-from-wcs-to-tapir.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Account Continuity | Migrated registered user can sign in with existing credentials | 1. Use a migrated pre-cutover account on the target storefront login page. 2. Authenticate without reset flow and continue to account area. | Login succeeds with existing credentials. No forced password reset appears for the migrated account.
UAT-002 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Account Profile | Core profile fields are visible and accurate after migration | Open account profile for migrated users and compare first name, last name, email, and date-of-birth values against legacy reference sample. | Core fields are populated and match expected legacy values. No corrupted or blank mandatory profile fields are observed.
UAT-003 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Consent Continuity | Consent states are preserved during migration | Review marketing/privacy/terms loyalty consent indicators in account settings for migrated users across both target brands. | Consent states match expected pre-migration records. No consent value is unexpectedly defaulted or lost.
UAT-004 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Continuity | Shipping and billing addresses appear for migrated users | Open address book for migrated accounts and validate at least one user with multiple addresses and one user with single address. | Expected addresses are present and linked to the correct account. No duplicate address cards are rendered for the same legacy address.
UAT-005 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Defaults | Default billing and shipping address flags are correct | For migrated users with historical defaults, inspect which address is marked default billing and default shipping after migration. | Default flags are correctly assigned. Only one default per type is active when expected by account data.
UAT-007 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Idempotency Outcome | Reprocessed migrated account set does not create visible duplicates | Use post-rerun sample accounts agreed with operations and re-check profile/address pages for duplicate account identity or duplicated address entities. | No duplicate account identity is visible. No duplicate address entities are introduced by reprocessing.
UAT-008 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Cross-brand Consistency | Migration outcomes are consistent across both acceptance storefronts | Execute key checks on both target URLs with equivalent migrated-user samples and compare behavior. | Critical migration outcomes are consistent across both environments. No brand-specific blocker is found for account or address continuity.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-16757 | AC-Profile-Migration | Registered user profile migration excluding passwords preserves core account attributes | High | UAT-002 | Full | AC and scenarios explicitly define profile-field mapping, consistency verification, and non-authentication data usage. | Unavailable | Functional | Story uses technical migration framing; business-facing UI verification steps are derived from expected outcomes.
COV-002 | G2-16757 | AC-No-Password-Transfer | No raw authentication credential transfer while preserving usable login continuity | High | UAT-001 | Partial | Story excludes password transfer but Epic intent requires successful credential continuity post-migration. | Unavailable | Regression | Credential continuity depends on dedicated password-hash mapping story and environment setup.
COV-003 | G2-16757 | AC-Idempotency-Update-Rules | Migration reprocessing respects update-date logic and avoids duplicates | High | UAT-007 | Full | Scenario 2 and 3 define no-duplicate behavior and conditional update logic based on export timing. | Unavailable | Regression | Back-office logs are primary technical proof; business UAT uses visible duplicate checks only.
COV-004 | G2-16757 | AC-Consent-Integrity | Customer consent information remains intact after migration | High | UAT-003, UAT-008 | Full | Epic and story scope include consent migration and completeness checks as key acceptance outcomes. | Unavailable | Functional | Consent-source parity must be cross-checked with business reference sample.
COV-005 | G2-18353 | AC-Address-Queue-Split | Address migration path is published independently from customer entities to support continuity | Medium | UAT-004 | Partial | AC defines separate address queue behavior and non-blocking invalid-address handling. | Unavailable | Integration | AC is queue-oriented; business UAT validates resulting address presence and stability rather than queue internals.
COV-006 | G2-18354 | AC-Address-Linking-Retry | Bulk address processor links addresses to the right customer and handles retries/default flags safely | High | UAT-004, UAT-005 | Full | Story AC and scenarios define customer-link lookup, retry behavior, create-vs-update handling, and default-flag management. | Unavailable | Functional | Comment indicates one scenario was initially ignored for bulk-only flow; follow-up indicates queue flow now covers ADD/UPDATE/DELETE.
COV-007 | G2-21527 | AC-PasswordHash-Compatibility | WCS passwordHashed mapping remains compatible with target encoder handling | High | UAT-001, UAT-008 | Partial | Task + Jira comment mention encoder-name variance (bcrypt vs argon2i), requiring representative login smoke checks. | Unavailable | Regression | No explicit PR/commit link in Jira metadata for this story despite completion comments.

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Jira Comment | G2-21527 | Password encoder-name variance was observed across migrated users (bcrypt vs argon2i). | Run sign-in smoke tests using a mixed sample of migrated accounts known to carry different hash-encoder origins. | Both cohorts authenticate successfully without forced reset. | High | COV-007,COV-002 | Derived from Jira comment by Yuri Reis on G2-21527.
EXP-002 | Jira Comment | G2-18354 | Address flow discussion evolved from bulk-create-only assumption to full ADD/UPDATE/DELETE support in queue system. | Sample migrated users with changed addresses and verify updates/deletes are reflected as expected in account address book. | Address update and delete outcomes are consistent with current implementation note. | Medium | COV-006 | Based on two Jira comments on G2-18354 clarifying scenario coverage.
EXP-003 | Jira AC Gap | G2-16757 | Story acceptance is heavily technical, with limited explicit storefront acceptance wording. | Use agreed business-user migrated-account sample sheet and verify profile, consent, address, and login continuity end-to-end. | Business-outcome checks pass even when backend metrics are not directly inspected by business users. | Medium | COV-001,COV-003,COV-004 | Derived from AC wording and scenario framing in G2-16757.