## Overview
G2-17473 UAT — Near Real-Time Address Sync WCS to Tapir
Epic Key | G2-17473
Epic Slug | wcs-tapir-address-sync
Generated Date | 2026-08-06
Epic Summary | Near real-time sync from WCS to Tapir - Addresses
Epic Status | Done
Created By | Cobbe, Valentina ¦¦ YOOX NET A PORTER
Component | CD1
Target URLs | Integ WCS (address change trigger), Acceptance Tapir Admin (sync verification target)
Estimated Timebox | 25-35 minutes
Coverage Summary | [Reduced V2 ~30% — 7/10 checks retained; AC coverage guardrail enforced] 3 UI-testable stories mapped to 10 business checks and 10 coverage rows. Bug G2-20787 (province sync regression, now Closed) informs regression scenario only.
Stories In Scope | G2-17012 ¦ Registered User Adds a New Address ¦ Done G2-17013 ¦ Registered User Updates an Address ¦ Done G2-17014 ¦ Registered User Deletes an Address ¦ Done
Stories Excluded | G2-20787 ¦ Province not updated in shipping address during sync ¦ Bug/defect ticket (Closed); informs exploratory regression scenario but is not a user story for direct UAT execution.
Out of Scope | Sync of non-registered (guest) users' addresses, WCS bulk import flows, Tapir Admin UI rendering completeness beyond address persistence, direct Tapir-to-WCS reverse address sync, and backend observability/monitoring validation.
Dev Evidence | GitHub MCP (org:mytheresa) search recovered merged PRs across two repos: tapir (Catalog Service, the Tapir target) and ant (Middleware between WCS and Tapir). G2-17012 (Add address): tapir#6419 'Add registered user add address endpoint' (merged 2025-11-21) + ant#37 'registered user adds a new address' (merged 2025-11-21). G2-17013 (Update address): ant#42 'update addresses' (merged 2025-12-05); the tapir-side update PR #6451 was closed UNMERGED (labeled 'do NOT merge'/'work in progress'), so the update path landed in the ant middleware. G2-17014 (Delete address): tapir#6489 'registered user deletes an address' (merged 2026-01-09, labels 'Contains Migrations','Porter' — includes a DB schema migration). Bug G2-20873 (clone of G2-20787): tapir#6634 'Improve handling of non-existing addresses in SyncAddressProcessor' (merged 2026-03-04) removed the non-blank requirement on addressId so a delete/sync for an address absent in Tapir no longer fails validation. No PR found for province-regression bug G2-20787. PR bodies for the add/update/delete stories use the boilerplate template (no per-field changelog); evidence is at endpoint/handler level. Story availability: G2-17012, G2-17013, G2-17014 Available; province regression Unavailable.
Gaps Summary | Add/update/delete PRs confirm the endpoints and middleware handlers exist, but their PR bodies are boilerplate (no explicit per-field mapping, address-type, or default-flag changelog) — those attribute checks remain evidenced only at AC level. No PR found for the province/state regression (G2-20787): province_name is stored in DB per developer comment but Tapir Admin UI display was unresolved at bug close; coverage deferred to exploratory scenario. tapir#6451 (update) was abandoned unmerged — verify the update path is fully served by the ant middleware (ant#42). Confluence page linked in G2-17013 (CD1 ¦ Analysis ¦ Customer Addresses Sync) not retrieved; AC from Jira remains canonical. Latency SLA (<5s) is defined at initiative level (G2-16119), not in child story AC.
Token Telemetry | payload_bytes=14429; payload_chars=14407; est_tokens~3602; checklist_rows=7; matrix_rows=7; exploratory_rows=3
Output Path | uat-test-plans-reduced30/G2-17473-wcs-tapir-address-sync.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Creation | Adding a new address via WCS MyAccount Address Book is synchronized to Tapir | 1. Log in to a registered user account on WCS. 2. Navigate to MyAccount > Address Book and add a new address with all required fields. 3. The WCS event is consumed by the ant middleware (ant#37) and posted to the Tapir add-address endpoint (tapir#6419). 4. Wait for sync, then inspect the address in Tapir (admin or API) to confirm the new record is present. | The new address appears in Tapir with matching street, city, postal code, region, and country values. Address is created without error and the sync completes without manual intervention.
UAT-002 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Creation | Adding a new address during WCS checkout (Shipping Details) is synchronized to Tapir | 1. Log in as a registered user on WCS. 2. Proceed to checkout and add a new shipping address in the Shipping Details step. 3. Complete or abandon the checkout flow. 4. The add-address event flows through the same ant#37 middleware handler to the tapir#6419 endpoint. 5. Verify the address exists in Tapir. | The new address entered during checkout is present in Tapir with all fields matching the input. Sync occurs without requiring additional user action after address entry.
UAT-003 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Update | Updating an existing address via WCS MyAccount Address Book is synchronized to Tapir | 1. Log in as a registered user on WCS. 2. Navigate to MyAccount > Address Book, select an existing address, and change at least one field (e.g., street or city). 3. Save the change. 4. The update event is processed by the ant middleware update-addresses path (ant#42). 5. Verify the updated address in Tapir; confirm the existing record is modified in place, not duplicated. | The updated field values are reflected in Tapir after sync. No duplicate address record is created; the existing record is modified in place.
UAT-006 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Data Completeness | All address fields are correctly mapped and persisted in Tapir after sync | 1. After any create or update sync operation, inspect the address in Tapir (via admin UI or API). 2. Verify each field: address line (street), city, postal code, region/state/province, and country. | All address fields match the source values from WCS exactly. No field is truncated, nulled, or incorrectly mapped during transit.
UAT-008 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Attributes | Address type (billing or shipping) is correctly identified and stored in Tapir after sync | 1. Create or update an address that is explicitly typed as billing on WCS. 2. Verify in Tapir that the address type field reflects the correct billing designation. | Address type (billing/shipping) in Tapir matches the type set on WCS. Switching address type on WCS correctly updates the type in Tapir on next sync.
UAT-009 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Address Attributes | Default address flag is preserved and correctly reflected in Tapir after sync | 1. Set an address as the default address in WCS MyAccount. 2. After sync, inspect the corresponding address record in Tapir and confirm the default flag is set. | The default address flag in Tapir matches the default designation on WCS. Only one address per user is marked as default in Tapir.
UAT-010 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Sync Latency | Address changes on WCS are reflected in Tapir in near real-time | 1. Perform an address create, update, or delete action on WCS and note the timestamp. 2. Inspect Tapir at 30-second intervals and record when the change appears. | Address change is visible in Tapir within a timeframe consistent with near real-time delivery (within minutes at most, targeting <5 seconds per initiative SLA). No manual trigger or batch job is required to initiate the sync.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-17012 | AC-Scenario1 | Address Creation via MyAccount Address Book | High | UAT-001 | Full | AC explicit: add new address in WCS Address Book → sync to Tapir. Evidence: tapir#6419 (add registered-user address endpoint, merged 2025-11-21) + ant#37 (WCS→Tapir middleware add-address handler, merged 2025-11-21). | Available | Functional | None
COV-002 | G2-17012 | AC-Scenario2 | Address Creation via Checkout Shipping Details | High | UAT-002 | Full | AC explicit: add new address in WCS checkout Shipping Details → sync to Tapir. Same implementation as COV-001: tapir#6419 add-address endpoint + ant#37 middleware handler (both merged 2025-11-21). | Available | Functional | None
COV-003 | G2-17013 | AC-Scenario1 | Address Update via MyAccount Address Book | High | UAT-003 | Full | AC explicit: update existing address in WCS Address Book → sync to Tapir. Evidence: ant#42 'update addresses' middleware PR (merged 2025-12-05). Tapir-side update PR #6451 was closed unmerged (WIP) — update path served by the ant middleware. | Available | Functional | None
COV-006 | G2-17473 | Epic-AC-FieldMapping | Address Field Completeness and Accuracy | High | UAT-006 | Full | Epic AC specifies data validated against WCS schema; all address line details must sync correctly. Field mapping is implemented within the add/update endpoints (tapir#6419, ant#37/#42); PR bodies are boilerplate so per-field mapping is not itemized — verify each field at runtime. | Available | Data Integrity | None
COV-008 | G2-17473 | Epic-AC-AddressType | Billing/Shipping Address Type Propagation | Medium | UAT-008 | Full | Epic AC explicitly lists address type (billing/shipping) as data to sync. | Unavailable | Data Integrity | None
COV-009 | G2-17473 | Epic-AC-DefaultFlag | Default Address Flag Propagation | Medium | UAT-009 | Full | Epic AC explicitly lists default address flag as data to sync. | Unavailable | Data Integrity | None
COV-010 | G2-17473 | Epic-AC-RealTime | Near Real-Time Sync Latency | High | UAT-010 | Partial | Epic AC states 'near real-time'; initiative G2-16119 defines <5 second SLA. Child story AC does not specify latency threshold explicitly. | Unavailable | Performance | Latency SLA defined at initiative level only; child story AC silent on specific threshold.

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Bug Context | G2-20787 / G2-20873 | Province/state field visible in Tapir Admin UI after sync | Update a WCS address with a non-null province/state value. After sync, check the Tapir Admin address detail page to confirm province/state is rendered in the UI (not only stored in the province_name DB column). | Province/state value is visible in the Tapir Admin address detail UI, matching the WCS source value. | If province/state is silently stored but not displayed in Admin UI, operations staff cannot verify address accuracy; customer service and fulfillment correctness risks. | COV-007 | G2-20787 developer comment: province correctly stored in province_name column but not exposed in Tapir Admin UI at time of bug analysis (Feb 2026). Bug closed but admin UI display gap noted.
EXP-002 | Bug Context | G2-20873 | WCS deletion of a non-existing Tapir address triggers DLQ handling | Send a delete-address event from WCS for an address ID that does not exist in Tapir. Observe the Ant/message queue behavior and confirm the event ends in DLQ rather than causing an unhandled error or loop. | The deletion message for a non-existing Tapir address is routed to the Dead Letter Queue without crashing the sync pipeline or blocking subsequent events. | Without proper DLQ handling, a delete event for a ghost/stale address could block the entire address sync queue or cause repeated retry storms. | COV-005 | G2-20873 (Closed bug, cloned from G2-20787): WCS deletion message of a non-existing Tapir address ends in DLQ. Confirmed by tapir#6634 (merged 2026-03-04) which removes the non-blank addressId validation requirement in SyncAddressProcessor so non-existing-address events are tolerated rather than erroring.
EXP-003 | Risk Analysis | G2-17473 | Sync ordering and idempotency under rapid consecutive address changes | Add a new address on WCS, then immediately update the same address before the first sync event lands in Tapir. Verify that the final state in Tapir reflects the most recent WCS state and no intermediate or phantom records are created. | Tapir address reflects only the final state from WCS. Events are processed in order or deduplicated such that no stale intermediate state is persisted. | Out-of-order event processing could leave Tapir with stale address data, causing fulfillment failures for customers who updated their address close to order placement. | COV-001, COV-002, COV-003, COV-004 | No explicit AC or evidence covers event ordering/idempotency. Gap identified from near-real-time event-driven architecture context.