## Overview
G2-17475 UAT - Near Real-Time Sync From WCS To Tapir Oblivion
Epic Key | G2-17475
Epic Slug | near-real-time-sync-from-wcs-to-tapir-oblivion
Generated Date | 2026-08-06
Epic Summary | Near real-time sync from WCS to Tapir - Oblivion
Epic Status | Backlog
Created By | Cobbe, Valentina ¦¦ YOOX NET A PORTER
Component | CD1
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 20-30 minutes
Coverage Summary | No child stories are directly linked to this epic. Coverage is enriched via the linked Initiative G2-16119 (Customer Data Synchronization – WCS to Tapir) which provides architectural context, latency SLA (< 5 seconds), data-scope definition, and links to 10+ Done sibling epics. Sibling Done stories G2-17014 (Registered User Deletes an Address, Done) and G2-17021 (Registered User Updates Email, Done, test result Nov-2025) confirm the event-driven WCS-to-Tapir/Gecco sync mechanism is implemented and tested. Coverage spans 6 checks: 4 epic-level AC checks plus 2 new checks derived from Initiative success criteria (latency SLA) and sibling implementation patterns (per-domain PII deletion).
Stories In Scope | No direct child stories. Initiative context: G2-16119 (Customer Data Synchronization – WCS to Tapir). Sibling Done stories used for evidence and pattern derivation: G2-17014 (Registered User Deletes an Address – under G2-17473 Addresses, Done), G2-17021 (Registered User Updates Email – under G2-17476 Email Changes, Done).
Stories Excluded | Sibling epics: G2-16317 (Newly created users), G2-16318 (Profile updates), G2-20372 (Wishlist), G2-17473 (Addresses), G2-17476 (Email Changes) – all Done and excluded from scope as they cover distinct event types. Reverse sync from Gecco to WCS (G2-22993).
Out of Scope | Story-level UI flows, technical implementation validation, reverse sync from Gecco to WCS (G2-22993), and non-PII data domains.
Dev Evidence | Available via Initiative context and sibling Done story evidence. G2-16119 (Initiative) links to 10+ Done sibling epics confirming the event-driven WCS-to-Gecco sync pipeline is implemented. G2-17014 (Registered User Deletes an Address, Done) confirms deletion propagation via the same sync mechanism. G2-17021 test result comment (Nov 2025) confirms sync is functional end-to-end including rejection of conflicting updates. Direct Bitbucket PR access blocked (unauthorized) – sibling story Done status and test results serve as Jira-link fallback evidence.
Gaps Summary | Oblivion event schema (full-customer deletion) differs from per-entity delete events used in sibling Done epics (G2-17014 deletes a single address). The oblivion trigger, event handler, and PII domain coverage matrix have not been enumerated in the epic ticket. Retry thresholds and SLA measurement points are not defined. Initiative success criteria (< 5s latency, 100% parity) apply but may need oblivion-specific tuning.
Token Telemetry | payload_bytes=12599; payload_chars=12583; est_tokens~3146; checklist_rows=6; matrix_rows=6; exploratory_rows=2
Output Path | uat-test-plans/G2-17475-near-real-time-sync-from-wcs-to-tapir-oblivion.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Deletion Propagation | Customer deletion initiated on WCS is reflected on Gecco in near real time | 1. Delete a test customer in WCS and confirm the customer profile is removed or anonymized in Gecco within expected sync latency. 2. The customer is matched via the parentCustomerUrn identity key established by the sync pipeline (tapir#6382 PorterMigrationMapping; ant#32 forwards ParentCustomerUrn on the message DTOs), so verify the oblivion event resolves to the correct internal customer before erasure. | Deletion/anonymization is reflected on Gecco after WCS deletion event. No residual active profile remains in Gecco for the deleted customer.
UAT-002 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Auditability | Oblivion event generates auditable confirmation of data removal | Execute an oblivion event and review available business-accessible logs or support-visible traces for confirmation records. | A traceable confirmation record exists for the deletion event. Record can be correlated to the customer and deletion timestamp.
UAT-003 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Retry Integrity | Partial or failed deletions are retried and converge to completed removal | Use a controlled failure scenario or replay path, then verify the retry mechanism processes the pending deletion to completion. | Retry process re-attempts failed deletion operations. Final state reaches complete deletion/anonymization without manual data patching.
UAT-004 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Data Scope Compliance | PII-associated data domains in scope are removed or anonymized consistently | For a deleted customer, inspect representative data domains (profile attributes, addresses, consents, credentials visibility) through accepted business verification paths. | In-scope personal data is removed or anonymized consistently across validated domains. No in-scope domain remains in an undeleted state after completion.
UAT-005 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Sync Latency | Oblivion event is reflected on Gecco within the near-real-time SLA defined in the initiative (< 5 seconds) | 1. Trigger a test customer deletion on WCS and measure the elapsed time until the deletion/anonymization is visible in Gecco. 2. Compare against the < 5-second SLA specified in G2-16119 Initiative success criteria. | Deletion is reflected on Gecco within 5 seconds of the WCS oblivion event. If latency exceeds the SLA, the retry mechanism picks up the event and the final state still converges within a reasonable window.
UAT-006 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Data Domain Coverage | Each PII data domain (profile attributes, address entries, consents, credentials/login link) is individually confirmed deleted or anonymized after an oblivion event | 1. After a test oblivion event, inspect each domain independently through available business verification paths: (1) profile attributes in Gecco, (2) address book entries, (3) marketing consents, (4) credential/login association. 2. Address-domain removal reuses the delete path proven in tapir#6489 (G2-17014); customer identity resolution uses the parentCustomerUrn mapping (tapir#6382 + ant#32). 3. Confirm the oblivion handler fans out to ALL four domains rather than relying on per-entity delete events. | Profile attributes are removed or anonymized. Address entries are removed. Consent records are removed or anonymized. Credential/login association is severed. No domain retains identifiable data after completion.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-17475 | AC-EPIC-001 | Deletion on WCS is propagated to Gecco | High | UAT-001 | Full | Deletion-propagation pattern evidenced by sibling tapir#6489 (registered user deletes an address, merged 2026-01-09, incl. DB migration) reused on the same WCS→Tapir/Gecco pipeline. Oblivion (full-customer) fan-out not yet decomposed at story level. | Available | Functional | No linked child stories for G2-17475 directly. Sibling Done story G2-17014 confirms deletion propagation pattern; oblivion-specific flow not yet decomposed at story level.
COV-002 | G2-17475 | AC-EPIC-002 | Deletion confirmation is logged and auditable | High | UAT-002 | Full | Mapped from epic acceptance criteria | Unavailable | Compliance | Audit log access path is not specified in the epic ticket. G2-16119 initiative requires full traceability but does not prescribe the audit mechanism.
COV-003 | G2-17475 | AC-EPIC-003 | Failed or partial deletion paths are retried | High | UAT-003 | Full | Mapped from epic acceptance criteria | Unavailable | Regression | Retry thresholds and timing are not defined in the epic text.
COV-004 | G2-17475 | AC-EPIC-004 | PII and associated attributes are removed or anonymized | High | UAT-004 | Partial | Mapped from data scope bullets in epic description | Unavailable | Security | Exact field-level deletion matrix is not enumerated in the epic ticket.
COV-005 | G2-16119 (Initiative context) | AC-INIT-001 | Oblivion event propagates within near-real-time latency SLA (< 5 seconds) | High | UAT-005 | Full | Latency SLA derived from G2-16119 Initiative success criteria. The event-driven pipeline meeting this SLA is evidenced by sibling PRs tapir#6382 + ant#32 (customer sync via parentCustomerUrn, merged 2025-11-13) and tapir#6489 (address delete, merged 2026-01-09). | Available | Performance | Oblivion events are full-customer deletes; latency profile may differ from incremental update events validated in sibling stories.
COV-006 | G2-16119 (Initiative context) + G2-17014 (sibling Done story) | AC-INIT-002 | All PII data domains are deleted or anonymized independently after an oblivion event | High | UAT-006 | Partial | Data-scope definition from G2-16119 (Personal Data, Attributes, Consents, Address Book). Address-domain deletion propagation is evidenced by tapir#6489 (G2-17014, merged 2026-01-09); customer identity mapping/anonymization key (parentCustomerUrn) by tapir#6382 + ant#32 (G2-17021). Oblivion-specific multi-domain fan-out not yet evidenced. | Available | Compliance | Oblivion-specific domain handler may not reuse per-entity delete events from sibling epics; confirmation of coverage for all 4 domains pending story breakdown.

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
OBS-001 | Jira Epic | G2-17475 | Epic is backlog-level and lacks linked child stories for concrete execution paths | Confirm with product/engineering owners whether implementation stories exist outside epic linkage and attach them before final sign-off. | Additional linked stories should refine scenario-level checks and evidence traceability. | Traceability | COV-001,COV-002,COV-003,COV-004 | No child stories returned by parent/epic-link/linked-issues hierarchy queries. Context enriched via linked Initiative G2-16119 and sibling Done stories G2-17014, G2-17021.
OBS-002 | Initiative + Sibling Done Stories | G2-16119, G2-17014, G2-17021 | Oblivion event handler may differ architecturally from per-entity delete events used in sibling Done epics | Confirm with engineering whether the oblivion trigger reuses the same WCS event bus / consumer as address and profile updates (G2-17014, G2-17021) or invokes a dedicated oblivion handler. Validate that the handler covers all 4 PII domains (profile, address, consent, credentials) rather than just a single entity type. | A dedicated oblivion consumer exists that orchestrates deletion across all PII domains, rather than delegating to per-entity handlers individually. | Coverage | COV-001,COV-004,COV-006 | Sibling story G2-17014 (address delete, Done) and G2-17021 (email update, Done – test result Nov 2025) confirm the pipeline works for single-entity events. Full-customer oblivion scope not yet validated at story level.