## Overview
G2-17566 UAT — Checkout Login & Registration & Guest Checkout
Epic Key | G2-17566
Epic Slug | checkout-login-registration-guest-checkout
Generated Date | 2026-08-06
Epic Summary | Checkout Login & Registration & Guest Checkout
Epic Status | Done
Created By | Cavazzuti, Matilde ¦¦ LuxExperience
Component | CA
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 30-40 minutes
Coverage Summary | 3 UI-testable FE stories mapped to 11 business checks and 20 coverage matrix rows.
Stories In Scope | G2-17571 ¦ FE: Checkout Login ¦ Done G2-17572 ¦ FE: Checkout Registration ¦ Done G2-18927 ¦ FE: Display email on guestForm email input if it exists on cart ¦ Done
Stories Excluded | None — all child stories are FE UI-testable.
Out of Scope | Backend authentication service internals, token expiry edge cases, third-party identity provider flows, performance and load testing, direct database verification.
Dev Evidence | QA comments on all 3 stories confirm AC met on both NAP and MRP (jira-comment source, Opalka, Aleksander ¦¦ YOOX NET A PORTER). No TRG-REL trigger fired; GitHub key search was not required. Dev evidence status: Available via jira-comment fallback for G2-17571, G2-17572, G2-18927.
Gaps Summary | G2-17572: T&C Link and consent Checkbox AC is marked TBC — behaviour should be verified against current legal/design specification before UAT sign-off. No Confluence doc linked for this epic. Wishlist merge behaviour on login is implied by cartId/wishlistId being sent in the mutation but is not explicitly AC-defined.
Token Telemetry | payload_bytes=17728; payload_chars=17708; est_tokens~4427; checklist_rows=11; matrix_rows=20; exploratory_rows=4
Output Path | uat-test-plans/G2-17566-checkout-login-registration-guest-checkout.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Login | Customer can log in during checkout using valid credentials | 1. Navigate to the checkout login step on NAP and MRP. 2. Enter a valid registered email and password. 3. Submit the login form. | Login succeeds and user is navigated to the shipping address step. The anonymous cart is preserved and associated with the logged-in session.
UAT-002 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Login | Checkout login shows error when credentials are invalid | 1. On the checkout login step, submit the form with an incorrect password for a known account. 2. Observe the page response. | An error notification is displayed. The customer remains on the login step and is not forwarded to shipping.
UAT-003 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Login | Email field validates format before submission | 1. Enter a malformed email address (e.g. 2. missing @) in the email field and attempt to submit. | Inline field validation error is displayed. Form does not submit until a correctly formatted email address is entered.
UAT-004 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Login | Anonymous cart is transferred to authenticated session on login | 1. Add items to cart as an anonymous user, proceed to checkout, log in at the login step. 2. Check cart contents after login. | Cart items added before login are visible in the post-login cart. Session continues seamlessly to the shipping address step.
UAT-005 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Registration | All required registration form fields are displayed | 1. Navigate to the checkout registration step on NAP and MRP. 2. Inspect the form visually. | Email, password, title dropdown, first name, and last name fields are all present. T&C link and consent checkbox are visible.
UAT-006 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Registration | Successful registration navigates customer to shipping address step | 1. Complete all registration fields with valid data and submit. 2. Observe the post-registration navigation on both NAP and MRP. | Account is created successfully. Customer is navigated directly to the shipping address step without additional prompts.
UAT-007 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Registration | Duplicate email address registration is rejected with an error | Attempt to register with an email address that is already associated with an existing account. | An error message is displayed indicating the email is already in use. Customer remains on the registration step and is not progressed.
UAT-008 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Registration | T&C consent checkbox is present and must be checked to submit | 1. Attempt to submit the registration form without checking the T&C checkbox. 2. Then check it and resubmit. | Form submission without T&C consent is blocked and an error is shown. With checkbox checked, submission proceeds normally.
UAT-009 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Registration | Registration form displays inline field errors for invalid inputs | 1. Submit the registration form with invalid or empty required fields (e.g. 2. blank first name, weak password). 3. Observe field-level feedback. | Each invalid field displays an inline error message. Form does not submit until all required fields pass validation.
UAT-010 | Cavazzuti, Matilde ¦¦ LuxExperience | Guest Checkout | Guest checkout email field is empty on first-time entry | 1. Start a fresh checkout session as a guest (no prior cart email stored). 2. Navigate to the guest email step. | The email input field is empty. Customer can enter their email and proceed to the address form.
UAT-011 | Cavazzuti, Matilde ¦¦ LuxExperience | Guest Checkout | Guest form pre-fills previously entered email and persists updates | 1. Enter an email as a guest and proceed to the address form. 2. Navigate back to the start of checkout, re-select guest option, and open the guest email form. 3. Update the email and navigate forward and back again. | On re-entry, the email field shows the previously entered address. After updating the email, the new address is shown on subsequent back-navigation.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-17571 | AC-1 | Checkout login email input field rendered | High | UAT-001 | Full | QA confirmed field present and functional on NAP and MRP (jira-comment, 2026-02-12). | Available | Positive
COV-002 | G2-17571 | AC-2 | Email format validation on checkout login | High | UAT-003 | Full | QA confirmed validation works (jira-comment, 2026-02-12). | Available | Negative
COV-003 | G2-17571 | AC-3 | Checkout login password input field rendered | High | UAT-001 | Full | QA confirmed field present and functional (jira-comment, 2026-02-12). | Available | Positive
COV-004 | G2-17571 | AC-4 | Successful login navigates to shipping address with cartId preserved | High | UAT-001, UAT-004 | Full | QA confirmed navigation and cart preservation (jira-comment, 2026-02-12). | Available | Positive
COV-005 | G2-17571 | AC-5 | Login error handling for invalid credentials and BE failure | High | UAT-002 | Full | QA confirmed incorrect credentials are rejected (jira-comment, 2026-02-12). | Available | Negative
COV-006 | G2-17572 | AC-1 | Registration email field rendered | High | UAT-005 | Full | QA confirmed form renders equivalently to dedicated registration page (jira-comment, 2026-02-12). | Available | Positive
COV-007 | G2-17572 | AC-2,AC-3,AC-4,AC-5 | Registration password, title, first name, last name fields rendered | High | UAT-005 | Full | QA confirmed all fields present on NAP and MRP (jira-comment, 2026-02-12). | Available | Positive
COV-008 | G2-17572 | AC-6 | T&C link and consent checkbox rendered and enforced | Medium | UAT-008 | Partial | AC marked TBC; behaviour not fully specified. QA comment does not explicitly confirm T&C enforcement. | Available | Positive | TBC marker in AC — T&C checkbox requirement should be confirmed against current legal/design specification before sign-off.
COV-009 | G2-17572 | AC-7 | Registration submission creates account and navigates to shipping | High | UAT-006 | Full | QA confirmed registration works and navigates forward (jira-comment, 2026-02-12). | Available | Positive
COV-010 | G2-17572 | AC-8 | wishlistId and cartId sent in registration mutation | Medium | UAT-006 | Partial | Backend mutation parameter; not explicitly confirmed in QA comment. Outcome is implied by cart continuity after registration. | Available | Positive | AC implies server-side mutation parameter — direct business validation is limited to cart continuity outcome.
COV-011 | G2-17572 | AC-9 | Registration form field error handling | High | UAT-009 | Full | QA confirmed form validation works (jira-comment, 2026-02-12). | Available | Negative
COV-012 | G2-17572 | AC-10 | Registration BE response failure error handling | High | UAT-007 | Full | QA confirmed duplicate email registration is rejected with error (jira-comment, 2026-02-12). | Available | Negative
COV-013 | G2-18927 | AC-1 | First-time guest checkout shows empty email input | High | UAT-010 | Full | QA confirmed email field empty on first entry (jira-comment, 2026-02-02). | Available | Positive
COV-014 | G2-18927 | AC-2 | Valid email entry proceeds to address form step | High | UAT-010 | Full | QA confirmed CTA proceeds to address form (jira-comment, 2026-02-02). | Available | Positive
COV-015 | G2-18927 | AC-3 | Back navigation returns to checkout start with guest option | Medium | UAT-011 | Full | QA confirmed back navigation shows checkout start step (jira-comment, 2026-02-02). | Available | Positive
COV-016 | G2-18927 | AC-4 | Re-opening guest form pre-fills previously entered email (editable) | High | UAT-011 | Full | QA confirmed email is prefilled with cart email and is editable (jira-comment, 2026-02-02). | Available | Positive
COV-017 | G2-18927 | AC-5 | Updated guest email persists correctly on subsequent navigation | High | UAT-011 | Full | QA confirmed new email is persisted and shown on re-entry (jira-comment, 2026-02-02). | Available | Positive
COV-018 | G2-17571 | AC-4 | Cross-brand login parity (NAP vs MRP) | High | UAT-001 | Full | QA explicitly confirmed behaviour is consistent on both NAP and MRP (jira-comment, 2026-02-12). | Available | Positive
COV-019 | G2-17572 | AC-7 | Cross-brand registration parity (NAP vs MRP) | High | UAT-006 | Full | QA confirmed registration flow works equivalently on both NAP and MRP (jira-comment, 2026-02-12). | Available | Positive
COV-020 | G2-17571, G2-17572 | AC-4,AC-7 | Post-auth checkout continuity — shipping step reached without interruption | High | UAT-001, UAT-006 | Full | QA confirmed both login and registration navigate directly to shipping step (jira-comment, 2026-02-12). | Available | Positive

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Cross-brand risk | G2-17571, G2-17572 | Brand-specific design differences in login/registration form layout or error messaging | Execute the login and registration flows side-by-side on NAP and MRP acceptance environments. Compare field labels, error messages, CTA text, and visual layout. | Forms are functionally identical; visual differences are limited to brand styling. Error messages are consistent and not brand-specific in wording. | Medium — inconsistent error messaging across brands degrades customer support and brand experience. | COV-018, COV-019 | QA comment confirms both brands pass; layout delta not documented.
EXP-002 | Auth continuity risk | G2-17571 | Cart items from anonymous session are not lost or duplicated on login | Add 2+ items to cart anonymously, proceed to checkout, log in, verify cart contents at the shipping step. Also test with a logged-in account that already has saved items. | Anonymous cart merges cleanly into the authenticated session. No items are lost or duplicated. | High — lost cart items on login would directly harm conversion. | COV-004 | QA comment notes cart is loaded post-login; explicit merge-conflict scenario not documented.
EXP-003 | Edge case | G2-17572 | Wishlist items are associated with newly registered account after checkout registration | As a guest with items in wishlist and cart, complete checkout registration. Post-registration, navigate to the wishlist page and verify items are preserved. | Wishlist items are associated with the new account. Cart continuity is maintained into shipping step. | Medium — wishlist loss after registration would reduce engagement. | COV-010 | AC states wishlistId is sent in registration mutation; no explicit QA confirmation of outcome.
EXP-004 | Edge case | G2-18927 | Guest email pre-fill does not interfere with a subsequent login flow selection | Enter a guest email, navigate to address form, navigate back, select login instead of guest. Verify that the login form does not pre-populate with the guest email. | Switching from guest to login mode shows a clean login form. Previously entered guest email does not bleed into the login email field. | Low — could cause confusion but does not block purchase. | COV-013, COV-016 | No specific AC or QA coverage for mode-switching scenario.