## Overview
G2-16248 UAT — Meganav Components & Set-up
Epic Key | G2-16248
Epic Slug | meganav-components-set-up
Generated Date | 2026-08-05
Epic Summary | NAP ¦ MRP ¦ Meganav Components & Set-up
Epic Status | Done
Created By | Sane, Sridevi Mayuresh ¦¦ LuxExperience
Component | D2
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 40-50 minutes
Coverage Summary | 17 UI-testable child stories/bugs/technical stories mapped to 11 business checks and 17 coverage rows. 10 backend, BO, evaluation, and QA task items excluded from business execution scope.
Stories In Scope | G2-16823 ¦ Story ¦ NAP ¦ Mobile Web ¦ Guest users: Build Mega Navigation Menu (top nav) (FE) ¦ Closed G2-17302 ¦ Story ¦ NAP ¦ Desktop ¦ Guest users: Build Mega Navigation Menu (top nav) - Part 1 (FE) ¦ Closed G2-17790 ¦ Story ¦ NAP ¦ MRP ¦ Component - Product Carousel on Meganav (FE) ¦ Closed G2-17796 ¦ Story ¦ NAP ¦ MRP ¦ Component - Content Blocks on Meganav (FE) ¦ Closed G2-17851 ¦ Story ¦ NAP ¦ Desktop ¦ Guest users: Build Mega Navigation Menu (top nav) - Part 2 - Clean-up (FE) ¦ Closed G2-17947 ¦ Story ¦ MRP ¦ Desktop, Mobile Web ¦ Guest users: Build Mega Navigation Menu (top nav) (FE) ¦ Closed G2-18710 ¦ Story ¦ NAP ¦ MRP ¦ Allow Red Text on Meganav and Nested PLP categories (FE) ¦ Closed G2-19002 ¦ Story ¦ NAP ¦ MRP ¦ Meganav Trending Designers Carousel (FE) ¦ Done G2-19618 ¦ Story ¦ NAP ¦ MRP ¦ Navigation No Flyout (FE) ¦ Closed G2-20396 ¦ Technical Story ¦ FE: UX Feedback on Meganav ¦ Done G2-20433 ¦ Bug ¦ NAP ¦ MRP ¦ Meganav UX Feedback - Product Carousel/ List (FE) ¦ Closed G2-20443 ¦ Bug ¦ MRP ¦ Meganav - Investigate & Update Nav Column Titles to Sackers (FE) ¦ Closed G2-20572 ¦ Bug ¦ NAP ¦ MRP ¦ Marketing Cards - UX Feedback Meganav (FE) ¦ Closed G2-20573 ¦ Bug ¦ NAP ¦ MRP ¦ Header&Nav - UX Feedback Meganav (FE) ¦ Closed G2-20612 ¦ Story ¦ NAP ¦ MRP ¦ Meganav Product Carousel - Integrate with Product Data (FE) ¦ Closed G2-21400 ¦ Story ¦ FE: Webmobile Navigation - Login/Register Button ¦ Done G2-22019 ¦ Story ¦ FE: Webmobile Navigation - Customer Service Links ¦ Done
Stories Excluded | G2-17310 ¦ Story ¦ NAP ¦ MRP ¦ Create MegaNav Templates (BE) ¦ Closed ¦ Backend template enablement; not directly customer-visible. G2-17735 ¦ Evaluation ¦ Investigate Mochi Development for New Templates (BO) ¦ Closed ¦ Investigation-only item with no user-facing acceptance flow. G2-17789 ¦ Story ¦ NAP ¦ MRP ¦ CMS Implementation to Support Product Carousel on MegaNav (BE) ¦ Done ¦ Backoffice/CMS backend implementation, validated indirectly via FE stories. G2-17941 ¦ Evaluation ¦ NAP ¦ MRP ¦ Investigate Product Carousel (BE/ API calls) (BE) ¦ Closed ¦ Investigation-only technical input; no standalone UAT path. G2-18798 ¦ Technical Story ¦ NAP ¦ MRP ¦ Tech debt: refactor header styling according to Atelier guidelines (FE) ¦ Closed ¦ Technical debt refactor with no explicit business acceptance path. G2-18837 ¦ Story ¦ NAP ¦ MRP ¦ Add the highlight flag on 2nd level of menu on Mochi (BO) ¦ Closed ¦ Backoffice configuration capability; not a direct customer-flow check for this plan. G2-20088 ¦ Technical Story ¦ NAP ¦ MRP ¦ Remove Forced Uppercase From Navigation Top Row Labels on Mochi (BO) ¦ Closed ¦ Backoffice/text transformation technical adjustment. G2-20569 ¦ Task ¦ QA ¦ Meganav E2E testing ¦ Done ¦ QA execution task; no new feature behavior. G2-20615 ¦ Story ¦ NAP ¦ MRP ¦ Meganav - Build Trending Designers Component in Mochi (BO) ¦ Done ¦ Backoffice component build; FE verification covered by G2-19002. G2-20617 ¦ Story ¦ NAP ¦ MRP ¦ Meganav - Create New template for Trending Designers (BE) ¦ Done ¦ Backend template creation; not directly business UAT executable.
Out of Scope | Backoffice authoring internals, BE template implementation details, and QA-runbook tasks that do not expose independent customer-facing behavior.
Dev Evidence | GitHub MCP commit search in mytheresa/atelier returned direct evidence for 15 in-scope stories. G2-17302 is Available via Jira comment GitHub URL fallback. G2-18710 remains Evidence Unavailable after GitHub + Jira fallback checks.
Gaps Summary | G2-18710 has no direct PR/commit hit by key and no Jira fallback PR/commit URL. UX feedback stories contain broad acceptance wording, so final sign-off should re-check spacing/typography states across desktop/mobile and both brands.
Token Telemetry | payload_bytes=17980; payload_chars=17978; est_tokens~4495; checklist_rows=11; matrix_rows=17; exploratory_rows=3
Output Path | uat-test-plans/G2-16248-meganav-components-set-up.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Desktop Main Navigation | Desktop top navigation opens and routes correctly for major categories | On NAP and MRP desktop, hover/click top-level categories and verify the expected first-level routing and flyout behavior. | Top-level categories open consistently on desktop. Category links route to the expected listing pages. No blocked or dead-end navigation state appears.
UAT-002 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Mobile Navigation | Mobile hamburger navigation exposes nested menu and closes/returns reliably | On mobile web for NAP and MRP, open hamburger menu, drill into nested levels, and navigate back/close repeatedly. | Menu opens and closes without visual breakage. Nested levels are reachable and reversible. Scroll and tap interactions remain stable during navigation.
UAT-003 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Flyout Templates | All configured flyout template variants render correctly | Validate no-flyout, text+image, and multi-column variants where configured in desktop and mobile contexts. | Configured template variant matches expected layout. No fallback-to-wrong-template behavior is observed. Content blocks render without overlap or clipping.
UAT-004 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Product Carousel | Product carousel and product-list style modules show valid data and interactions | Open navigation entries with product carousel/list content and verify item load, image rendering, and click-through behavior. | Product data is populated with valid items. Item click-through opens the correct product page. Carousel/list visuals align with active brand styling.
UAT-005 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Trending Designers | Trending designers module is visible and navigable where configured | Verify the trending designers section appears in configured meganav nodes and links resolve as intended. | Module is rendered in configured positions. Designer links are clickable and route correctly. Module styling remains consistent across brands.
UAT-006 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | No-Flyout Behavior | Navigation supports no-flyout categories without empty overlays | Open categories configured as no-flyout and confirm no blank flyout panel appears. | No-flyout items route directly without showing empty panels. Header state remains stable after repeated navigation.
UAT-007 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | UX Feedback Fixes | UX feedback fixes for spacing, typography, and card layout are reflected in navigation | Review corrected areas from UX feedback tickets, including title spacing, card spacing, and header/navigation visual details. | Agreed spacing and typography adjustments are visible. Marketing cards and navigation titles match intended presentation. No major regressions appear in corrected areas.
UAT-008 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Cross-Brand Variants | Brand-specific style exceptions are preserved between NAP and MRP | Compare the same meganav structures in NAP and MRP and confirm expected visual deltas are present while behavior remains equivalent. | Brand-specific visual differences appear only where intended. Functional navigation behavior remains equivalent across brands. No cross-brand asset leakage is visible.
UAT-009 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Mobile Auth Entry | Mobile login/register entry point is present and routes correctly for guests | On mobile web, verify guest users can access login/register from navigation and return to browsing state after navigation. | Login/Register entry is visible for guests. Tap action routes to authentication flow correctly. Returning from auth does not break menu state.
UAT-010 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Mobile Service Links | Customer service links are available and correctly mapped in mobile navigation | Open account/service area from mobile menu and validate customer service link presence, labels, and destinations. | All expected service links are present. Each link routes to the intended destination. Spacing and hover/active states are acceptable.
UAT-011 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Regression Sanity | Meganav changes do not regress core browse journey from homepage to PLP/PDP | Execute a short browse journey for both brands from homepage through category to product page using meganav entry points. | Journey completes without broken navigation transitions. No severe UI regressions block browsing. Core pages remain reachable from updated meganav.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-16823 | AC-MWeb-TopNav | Mobile top navigation foundation for guest users | High | UAT-002,UAT-011 | Full | PR #163 from GitHub MCP. | Available | Functional
COV-002 | G2-17302 | AC-Desktop-TopNav | Desktop top navigation base interactions for NAP | High | UAT-001,UAT-011 | Full | No direct key commit hit; Jira comment contains GitHub compare URL fallback. | Available | Functional
COV-003 | G2-17790 | AC-Carousel-Render | Product carousel component in meganav | High | UAT-004 | Full | PR #314 from GitHub MCP. | Available | Functional
COV-004 | G2-17796 | AC-ContentBlocks-Render | Content block component rendering in meganav flyout | High | UAT-003,UAT-011 | Full | PR #242 from GitHub MCP. | Available | Functional
COV-005 | G2-17851 | AC-Desktop-Cleanup | Desktop top nav cleanup and behavioral stability | Medium | UAT-001,UAT-011 | Full | PR #152 from GitHub MCP. | Available | Regression
COV-006 | G2-17947 | AC-MRP-Desktop-Mobile | MRP desktop/mobile meganav parity with expected routes | High | UAT-001,UAT-002,UAT-008 | Full | PR #209 from GitHub MCP. | Available | Functional
COV-007 | G2-18710 | AC-RedText-Highlight | Red text support in meganav and nested categories | Medium | UAT-007,UAT-008 | Partial | No key-based GitHub hit and no Jira fallback PR/commit URL. | Evidence Unavailable | UX | Implementation evidence gap despite clear business expectation.
COV-008 | G2-19002 | AC-Trending-Designers | Trending designers carousel in meganav | Medium | UAT-005 | Full | PR #456 from GitHub MCP. | Available | Functional
COV-009 | G2-19618 | AC-NoFlyout | No-flyout navigation behavior | High | UAT-006 | Full | PR #299 from GitHub MCP. | Available | Functional
COV-010 | G2-20396 | AC-UX-Feedback-Bundle | Consolidated UX review fixes on meganav/header | High | UAT-007,UAT-011 | Partial | PR #501 from GitHub MCP; AC phrasing spans multiple visual defects. | Available | Regression | Broad ticket scope may hide per-defect acceptance granularity.
COV-011 | G2-20433 | Bugfix-Carousel-UX | Product carousel/list UX corrections | Medium | UAT-004,UAT-007 | Full | PR #395 from GitHub MCP. | Available | Regression
COV-012 | G2-20443 | Bugfix-MRP-Title-Styling | MRP nav column title styling exceptions | Medium | UAT-007,UAT-008 | Full | PR #438 from GitHub MCP; Jira comment references discussion #424. | Available | UX
COV-013 | G2-20572 | Bugfix-Marketing-Cards | Marketing card spacing/layout corrections in meganav | Medium | UAT-007 | Full | PR #367 from GitHub MCP. | Available | Regression
COV-014 | G2-20573 | Bugfix-Header-Nav-UX | Header and nav UX adjustment bundle | Medium | UAT-007,UAT-011 | Full | PR #373 from GitHub MCP. | Available | Regression
COV-015 | G2-20612 | AC-Carousel-Data-Integration | Product carousel integration with real product data | High | UAT-004 | Full | PR #420 from GitHub MCP. | Available | Functional
COV-016 | G2-21400 | AC-Mobile-Auth-Entry | Login/Register entry in mobile navigation for guests | High | UAT-009 | Full | PR #516 from GitHub MCP. | Available | Functional
COV-017 | G2-22019 | AC-Mobile-Service-Links | Customer service link group in mobile navigation | High | UAT-010 | Full | PR #552 from GitHub MCP. | Available | Functional

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Confluence | G2-16248 | Confluence Meganav page indicates scenario variance across NAP/MRP and desktop/mobile screenshot sets. | Run side-by-side NAP and MRP checks for main categories, designers, and content block rows on desktop and mobile. | Expected brand-specific visual differences remain intentional while interaction behavior remains equivalent. | Medium | COV-001,COV-006,COV-010 | Confluence page id 186974482 and page 186976112 were retrieved from GEC space search.
EXP-002 | AC Ambiguity | G2-20396 | UX-feedback bundle combines multiple visual fixes under one ticket, increasing acceptance ambiguity. | Use focused before/after screenshots for each corrected area and sign off each area independently. | All listed visual defects are closed without introducing new regressions. | Medium | COV-010,COV-011,COV-013,COV-014 | Technical Story with broad AC wording; PR evidence available but per-defect mapping is coarse.
EXP-003 | Evidence Gap | G2-18710 | Red text support has business relevance but no direct development evidence found by key or Jira fallback. | Prioritize manual visual check on sale/promotional entries with red text in meganav and nested categories. | Red text appears only where configured and preserves readability/contrast standards. | High | COV-007 | GitHub key search returned zero commit hits and Jira comments lacked PR/commit links.