## Overview
G2-16283 UAT - Colour linking
Epic Key | G2-16283
Epic Slug | colour-linking
Generated Date | 2026-08-05
Epic Summary | Colour linking
Epic Status | Done
Created By | Kozlova, Nika ¦¦ External
Component | D3
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 35-45 minutes
Coverage Summary | 4 UI-testable child stories mapped to 8 business checklist checks and 8 coverage rows. 8 child items were excluded as backend-only, spike, or technical non-business execution scope.
Stories In Scope | G2-18020 ¦ Technical Story ¦ FE ¦ WL ¦ MiniPDP Colour Selection Component ¦ Closed G2-18366 ¦ Story ¦ FE ¦ Mini PDP Color Variants ¦ Done G2-19715 ¦ Technical Story ¦ FE ¦ UI Implement alternativeColours on PDP ¦ Done G2-21838 ¦ Story ¦ FE ¦ PDP ¦ Colour picker scroll ¦ Done
Stories Excluded | G2-16519 ¦ Evaluation ¦ [SPIKE] BE ¦ Colour swatches gaps analysis ¦ Done ¦ Research spike; not a direct storefront UAT execution item. G2-19161 ¦ Technical Story ¦ BE ¦ TAPIR ¦ Create Alternative Colours Porter endpoint ¦ Done ¦ Backend-only endpoint work. G2-19162 ¦ Technical Story ¦ BE ¦ HYENA ¦ Create alternativeColours Porter query ¦ Done ¦ Backend-only query work. G2-19369 ¦ Technical Story ¦ FE ¦ Implement alternativeColours graphql query ¦ Done ¦ FE integration plumbing without direct business acceptance path. G2-20887 ¦ Technical Story ¦ BE ¦ Optimize Alternative Color Payload for PDP Swatch Rendering ¦ Done ¦ Performance/internal backend optimization. G2-21051 ¦ Evaluation ¦ [SPIKE] FE ¦ Investigate Global state manager solution ¦ Done ¦ Architectural investigation. G2-21632 ¦ Task ¦ BE ¦ HYENA ¦ Refactor alternative colors resolver for xProduct ¦ Done ¦ Backend refactor task. G2-21642 ¦ Task ¦ FE ¦ PDP ¦ Optimize Alternative Color Product Loading ¦ Done ¦ Technical performance task, not business-step validation.
Out of Scope | Backend resolver internals, GraphQL schema-level validation, low-level performance profiling, and non-functional refactor acceptance not executable as business quick checks.
Dev Evidence | Available for 3/4 in-scope stories via GitHub commit search (mytheresa/atelier). G2-18020 has no direct PR/commit hit after GitHub org-wide search and Jira-link fallback scan, so it remains Evidence Unavailable.
Gaps Summary | G2-18020 includes high-level AC and comments indicating completion in prior tickets, but direct development evidence keyed to G2-18020 was not found. Confluence page 131311901 was reachable but is mostly backend flow context and not a direct AC source for MiniPDP/PDP color-interaction behavior.
Token Telemetry | payload_bytes=11392; payload_chars=11392; est_tokens~2848; checklist_rows=8; matrix_rows=8; exploratory_rows=3
Output Path | uat-test-plans/G2-16283-colour-linking.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Kozlova, Nika ¦¦ External | MiniPDP Entry | Open MiniPDP from wishlist and confirm preselected color variant | From wishlist, open MiniPDP for an item with multiple colors and inspect initial state before interaction. | MiniPDP opens successfully from wishlist item. Current item color is preselected by default. No unexpected size preselection occurs.
UAT-002 | Kozlova, Nika ¦¦ External | Color Switching | Switch MiniPDP color swatches and verify image and size-state updates | In MiniPDP, choose a different color swatch and observe image refresh and size availability state changes. | Selected swatch updates the active product image. Size availability reflects selected color state. MiniPDP remains open during color switching.
UAT-003 | Kozlova, Nika ¦¦ External | A2B and A2W | Validate add-to-bag and add-to-wishlist actions after color change | 1. After selecting a new color and size, add to bag 2. repeat add-to-wishlist into selected list and observe duplicate handling. | Add-to-bag succeeds for available size. Add-to-wishlist applies to selected list. Duplicate-add attempt displays expected warning without state corruption.
UAT-004 | Kozlova, Nika ¦¦ External | PDP Swatch Rendering | Verify alternative color selector renders on PDP | 1. Open PDP items with one, two, and many colors 2. verify swatch list visibility and selected-state indicator. | Alternative color selector is visible for applicable items. Selected swatch has clear active indicator. Single-color and multi-color cases render consistently.
UAT-005 | Kozlova, Nika ¦¦ External | Horizontal Scroll | Use vertical mouse wheel to horizontally scroll color picker on desktop | On desktop PDP where swatches overflow viewport width, use vertical wheel while pointer is over swatch rail. | Swatch rail moves horizontally with vertical wheel input. User can reach off-screen swatches without auxiliary devices. Interaction remains smooth without freeze.
UAT-006 | Kozlova, Nika ¦¦ External | Cross-Brand Behavior | Confirm color-selection behavior parity on NAP and MRP acceptance | Repeat key MiniPDP/PDP swatch flows on both brand acceptance environments and compare outcomes. | Core color interaction behavior is equivalent across brands. No brand-specific blocker appears in basic selection flow.
UAT-007 | Kozlova, Nika ¦¦ External | Responsive Behavior | Validate desktop/mobile interaction expectations for color picker | 1. Run MiniPDP and PDP color checks in desktop and mobile breakpoints 2. confirm desktop wheel behavior and mobile swipe fallback. | Desktop supports wheel-driven horizontal navigation where specified. Mobile supports touch swipe navigation for swatches. No critical interaction regression across breakpoints.
UAT-008 | Kozlova, Nika ¦¦ External | Data Robustness | Exercise products with different color-count datasets | 1. Use acceptance products covering one, two, three, and many-color scenarios from Jira test notes 2. execute core color-switch journey. | All sample datasets are navigable. No broken swatch state appears for higher color counts. Journey remains stable for color and size selection.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-18020 | AC-MINIPDP-COMPONENT | MiniPDP colour selection component baseline behavior | High | UAT-001,UAT-002 | Partial | Jira AC present; comments indicate implementation completed via prior tickets. No direct commit/PR hit for G2-18020 after GitHub and Jira-link fallback scans. | Evidence Unavailable | Functional | Story references prior-ticket completion; direct traceability requires linked implementation key confirmation.
COV-002 | G2-18366 | AC-MINIPDP-COLOR-VARIANTS | MiniPDP color variant selection and image update | High | UAT-001,UAT-002,UAT-003 | Full | GitHub commit: https://github.com/mytheresa/atelier/commit/1d5f496b67f05e4a2fae3e31cf0ccca78b7a6e05 | Available | Functional
COV-003 | G2-18366 | AC-MINIPDP-A2B-A2W | MiniPDP add-to-bag and add-to-wishlist continuity after color switch | High | UAT-003 | Full | Derived from Jira AC scenarios and acceptance test comments. | Available | Regression
COV-004 | G2-19715 | AC-PDP-ALT-COLORS | Alternative colours component visible on PDP | High | UAT-004 | Full | GitHub commit: https://github.com/mytheresa/atelier/commit/609388c47f7551469063e77bf8f417216462fe7d | Available | Functional
COV-005 | G2-21838 | AC-PDP-HSCROLL-WHEEL | Horizontal swatch scroll with vertical wheel input on desktop | High | UAT-005 | Full | GitHub commit: https://github.com/mytheresa/atelier/commit/df1b2a394c27dcdf998b0eb79f0460d6442dab33 | Available | Functional
COV-006 | G2-18366 | AC-CROSS-BRAND | Cross-brand execution on NAP and MRP | Medium | UAT-006 | Full | Jira AC explicitly references NAP and MRP. | Available | Compatibility
COV-007 | G2-18366,G2-21838 | AC-RESPONSIVE | Desktop and mobile interaction parity for swatches | Medium | UAT-007 | Partial | Desktop/mobile notes in Jira AC and test comments; no dedicated mobile-specific implementation ticket surfaced in this epic map. | Available | UX
COV-008 | G2-19715,G2-21838 | AC-DATASET-ROBUSTNESS | Color picker stability across variable color-count products | Medium | UAT-008 | Partial | Jira comments include acceptance test products with different color counts. | Available | Regression

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Evidence Gap | G2-18020 | Direct development evidence for G2-18020 is missing despite completed status. | Trace linked or predecessor Jira keys and verify whether implementation was merged under a different ticket key. | A predecessor implementation key is identified and linked back for full traceability. | Medium | COV-001 | GitHub search by key in repo and org returned no hits; Jira comments indicate prior-ticket completion.
EXP-002 | Confluence Context | G2-16283 | Confluence page 131311901 is accessible but mostly backend data-flow context, not direct UI acceptance guidance. | Confirm if additional UI-focused Confluence documents exist for color linking behavior in MiniPDP/PDP. | Either a UI-focused doc is linked or Jira AC remains the canonical test source. | Low | COV-004,COV-005 | Content title: Product bundles new flow activation.
EXP-003 | Risk Note | G2-19715 | Ticket comments mention temporary FE bugs until data cleanup task completion. | Run color-switch checks on acceptance with known test products and capture any residual data anomalies. | UI remains stable with no critical blocker after cleanup dependencies are complete. | Medium | COV-004,COV-008 | Comment references dependency on G2-20655 data cleanup.