## Overview
G2-16477 UAT - Shipping Address
Epic Key | G2-16477
Epic Slug | shipping-address
Generated Date | 2026-08-05
Epic Summary | Shipping Address
Epic Status | Done
Created By | Cavazzuti, Matilde ¦¦ LuxExperience
Component | CA
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 40-50 minutes
Coverage Summary | 27 UI-testable stories mapped to 12 business checks and 27 coverage rows. 10 non-UI/backend/evaluation stories are excluded from direct business execution.
Stories In Scope | G2-24110 ¦ FE: Handle Shipping Address Validation errors from BE ¦ Done G2-24107 ¦ FE: Investigate how to consume addressConfigs.json from local when running app locally ¦ Done G2-24101 ¦ FE: Validate saved Shipping Address ¦ Closed G2-23676 ¦ FE: Update Title list on Address Form ¦ Closed G2-23608 ¦ FE: Implement correct provinces (state) handling ¦ Done G2-23235 ¦ FE: Address Form for UK is missing county code ¦ Closed G2-22963 ¦ FE: Fix Checkbox Accessibility Issues ¦ Done G2-22962 ¦ FE: Fix Address Form-related Accessibility Issues ¦ Done G2-22945 ¦ FE: Send optional field phoneNumberAlternate on xUpdateCartAddress and xAddAddressToUser ¦ Done G2-22747 ¦ FE: Alternate phone number field hidden ¦ Done G2-22710 ¦ FE: Improve Address List Handling ¦ Closed G2-22590 ¦ FE: Prevent Saving Duplicated Address In Shipping Address Step ¦ Done G2-21951 ¦ FE: Address Form Skeleton and SSR ¦ Done G2-21547 ¦ FE: Address Autocompletion ¦ Done G2-19646 ¦ FE: Address Form Fields Validation ¦ Done G2-19645 ¦ FE: Address Form Fields Rendering ¦ Done G2-19644 ¦ FE: Address Form Data Model Integration ¦ Done G2-19343 ¦ FE: Remove house number splitting ¦ Closed G2-19222 ¦ FE: Fix select component's responsive height ¦ Done G2-19115 ¦ FE: Edit Shipping Address ¦ Done G2-19114 ¦ FE: Shipping Address selection ¦ Done G2-19113 ¦ FE: Shipping Address Country ¦ Done G2-18989 ¦ FE: Small Misalignments of Atelier vs MRP&NAR real impl. ¦ Closed G2-18988 ¦ FE: Invisible characters - Extended trimming for shipping address validation. ¦ Done G2-18559 ¦ FE: "Continue to checkout" btn redirect screen movement ¦ Closed G2-17909 ¦ FE: Checkout route logic ¦ Done G2-17569 ¦ FE: Shipping Address form (dynamic) ¦ Closed
Stories Excluded | G2-23772 ¦ BE: Update Title Validation for Address Form based on the new list ¦ Backend-only validation update not directly executable by business users. G2-23596 ¦ BE: Implement correct provinces (state) handling ¦ Backend-only province handling implementation. G2-23549 ¦ BE: Update Last Name Validation ¦ Backend-only validation rule change. G2-23344 ¦ BE: Allow empty state field for countries where the province is optional ¦ Backend bugfix for optional state handling. G2-22944 ¦ BE: Accept optional field alternativePhoneNumber on xUpdateCartAddress and xAddAddressToUser/xUpdateUserAddress ¦ Backend API contract task not UI-executable. G2-22682 ¦ BE: MRP ¦ Checkout blocked for new shipping address ¦ Backend checkout blocking defect resolution. G2-22591 ¦ BE: Prevent Duplicating Address On Successful Payment ¦ Backend duplicate-address prevention implementation. G2-21751 ¦ FE Spike ¦ Address Autocompletion ¦ Evaluation spike; discovery activity without deterministic UAT AC. G2-19648 ¦ FE Spike ¦ Address Form Data Structure ¦ Evaluation spike for data structure discovery. G2-19260 ¦ Spike ¦ Dynamic Address Forms using Address Validation ¦ Architecture spike for dynamic forms; non-UI delivery story.
Out of Scope | Backend service internals, API contracts, and engineering-only spike outcomes that cannot be directly validated by business users in storefront checkout.
Dev Evidence | Trigger summary: triggered stories=24/27; GitHub lookups executed=0; Confluence lookups executed=1 (Epic-level documentation link only). Jira-link fallback scan on in-scope stories found no GitHub PR/commit URLs. Evidence status: Evidence Unavailable for all in-scope stories.
Gaps Summary | Story-level AC quality is uneven: multiple technical/tasks rely on implementation intent with limited business edge-case acceptance wording. No direct PR/commit evidence discovered via Jira-link fallback; release-readiness confidence depends on execution of checkout negative paths and cross-brand regression checks.
Token Telemetry | payload_bytes=23950; payload_chars=23950; est_tokens~5988; checklist_rows=12; matrix_rows=27; exploratory_rows=3
Output Path | uat-test-plans/G2-16477-shipping-address.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cavazzuti, Matilde ¦¦ LuxExperience | Shipping Address Entry | Customer can add a new shipping address with mandatory fields | Open Checkout shipping step as guest and logged-in user, choose add new address, fill mandatory fields and submit. | Address saves successfully and step can continue. No blocking validation error is shown for valid data.
UAT-002 | Cavazzuti, Matilde ¦¦ LuxExperience | Dynamic Country Rules | Address form changes by selected shipping country | Change country selector in shipping step and inspect field labels, optionality, and max-length behavior. | Field set and validation hints update according to selected country. Country-specific constraints are visible before submit.
UAT-003 | Cavazzuti, Matilde ¦¦ LuxExperience | Saved Address Selection | Customer can select a saved shipping address and continue | Login with account with multiple saved addresses, select each candidate address, and attempt to continue. | Valid saved address is accepted and checkout proceeds. Invalid saved address cannot proceed without correction.
UAT-004 | Cavazzuti, Matilde ¦¦ LuxExperience | Saved Address Edit | Customer can edit an existing saved shipping address | From shipping address list, edit a saved address, change data, confirm, and continue checkout. | Edited address is persisted and selected for the order. Customer can cancel edit and keep another valid address.
UAT-005 | Cavazzuti, Matilde ¦¦ LuxExperience | Server Validation Errors | Backend validation errors are mapped to field-level messages | Submit address values that trigger server-side validation and observe returned error handling in form UI. | Address form remains visible with field-level error state. Customer cannot continue until invalid values are corrected.
UAT-006 | Cavazzuti, Matilde ¦¦ LuxExperience | Autocomplete | Address autocompletion suggests and fills address data | Type searchable address prefix in supported country and pick a suggestion. | Suggestion list appears promptly and selected suggestion populates related fields. Manual override remains possible before submit.
UAT-007 | Cavazzuti, Matilde ¦¦ LuxExperience | Phone Fields | Phone and alternate phone optional/required behavior is correct | Validate primary phone rules and alternate phone handling while adding/updating addresses. | Primary phone validation follows configured constraints. Optional alternate phone is accepted when provided and ignored when omitted.
UAT-008 | Cavazzuti, Matilde ¦¦ LuxExperience | Accessibility | Keyboard/focus/error accessibility for address step works | Navigate form using keyboard only, trigger errors, and validate focus and aria/readability behavior. | Interactive controls are reachable and understandable by keyboard users. Validation states are perceivable and actionable.
UAT-009 | Cavazzuti, Matilde ¦¦ LuxExperience | Trimming and Input Hygiene | Invisible characters and trimming are handled safely | Paste values with extra spaces/invisible characters in address fields and submit. | Values are sanitized according to rules without corrupting user intent. Validation outcome is consistent after trimming.
UAT-010 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Routing | Continue/back routing in shipping step preserves state | Use continue/back actions around shipping step, including redirect edge cases, and re-open shipping step. | Navigation does not lose valid address state unexpectedly. Customer returns to the expected checkout step.
UAT-011 | Cavazzuti, Matilde ¦¦ LuxExperience | Cross-Brand/Desktop-Mobile | Core shipping-address flow is consistent across brands and devices | Run critical checks on both target storefronts and on desktop/mobile viewports. | Core address behaviors and blocking validations are consistent. No brand/device-specific blocker is observed in core flow.
UAT-012 | Cavazzuti, Matilde ¦¦ LuxExperience | Address Save and Duplication Guard | Saving behavior avoids accidental duplicate addresses | Submit same logical address multiple times through add/edit paths and inspect resulting address book/selection list. | No unintended duplicate address entries are introduced by checkout flow. Order proceeds with the intended selected address.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-24110 | AC-G2-24110 | Handle Shipping Address Validation errors from BE | High | UAT-005 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-002 | G2-24107 | AC-G2-24107 | Investigate how to consume addressConfigs.json from local when running app locally | Medium | UAT-001 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-003 | G2-24101 | AC-G2-24101 | Validate saved Shipping Address | High | UAT-001 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-004 | G2-23676 | AC-G2-23676 | Update Title list on Address Form | High | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-005 | G2-23608 | AC-G2-23608 | Implement correct provinces (state) handling | High | UAT-001 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-006 | G2-23235 | AC-G2-23235 | Address Form for UK is missing county code | High | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-007 | G2-22963 | AC-G2-22963 | Fix Checkbox Accessibility Issues | Medium | UAT-008 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Regression | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-008 | G2-22962 | AC-G2-22962 | Fix Address Form-related Accessibility Issues | Medium | UAT-008 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Regression | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-009 | G2-22945 | AC-G2-22945 | Send optional field phoneNumberAlternate on xUpdateCartAddress and xAddAddressToUser | Medium | UAT-007 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-010 | G2-22747 | AC-G2-22747 | Alternate phone number field hidden | Medium | UAT-007 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-011 | G2-22710 | AC-G2-22710 | Improve Address List Handling | High | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-012 | G2-22590 | AC-G2-22590 | Prevent Saving Duplicated Address In Shipping Address Step | High | UAT-012 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-013 | G2-21951 | AC-G2-21951 | Address Form Skeleton and SSR | High | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-014 | G2-21547 | AC-G2-21547 | Address Autocompletion | High | UAT-006 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-015 | G2-19646 | AC-G2-19646 | Address Form Fields Validation | High | UAT-005 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-016 | G2-19645 | AC-G2-19645 | Address Form Fields Rendering | Medium | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-017 | G2-19644 | AC-G2-19644 | Address Form Data Model Integration | Medium | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-018 | G2-19343 | AC-G2-19343 | Remove house number splitting | Medium | UAT-001 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-019 | G2-19222 | AC-G2-19222 | Fix select component's responsive height | Medium | UAT-001 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-020 | G2-19115 | AC-G2-19115 | Edit Shipping Address | High | UAT-004 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-021 | G2-19114 | AC-G2-19114 | Shipping Address selection | High | UAT-003 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-022 | G2-19113 | AC-G2-19113 | Shipping Address Country | High | UAT-002 | Partial | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | No explicit conflict detected; some stories provide limited edge-case detail.
COV-023 | G2-18989 | AC-G2-18989 | Small Misalignments of Atelier vs MRP&NAR real impl. | Medium | UAT-001 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-024 | G2-18988 | AC-G2-18988 | Invisible characters - Extended trimming for shipping address validation. | High | UAT-005 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-025 | G2-18559 | AC-G2-18559 | "Continue to checkout" btn redirect screen movement | Medium | UAT-010 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Regression | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-026 | G2-17909 | AC-G2-17909 | Checkout route logic | Medium | UAT-010 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.
COV-027 | G2-17569 | AC-G2-17569 | Shipping Address form (dynamic) | High | UAT-002 | Inferred | Jira description/comments/issuelinks scan: no GitHub PR/commit URL found | Evidence Unavailable | Functional | Acceptance criteria are sparse or absent; behavior inferred from story goal/title.

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Jira AC Gap | G2-16477 | Several implementation-focused FE tasks provide limited end-user edge-case AC detail. | Run negative-path combinations for country/state optionality, saved-address correction, and server-side validation failures. | Errors are field-specific, recoverable, and do not trap users in checkout. | High | COV-001,COV-003,COV-006,COV-015 | Derived from Epic and child-story AC density review.
EXP-002 | Confluence Link | G2-16477 | Loqate overview link suggests dependency on external autocomplete behavior and environment readiness. | Validate autocomplete enablement per environment and confirm graceful manual-entry fallback when suggestion quality is low. | Autocomplete assists entry without blocking manual completion. | Medium | COV-014,COV-019 | Based on Epic useful documentation reference.
EXP-003 | Cross-Brand Risk | G2-19113,G2-17569 | Country-switch and dynamic-form behavior may diverge across storefront variants and viewport sizes. | Execute country-change plus form-submit journeys on both target URLs in desktop and mobile. | No brand-specific blocker and consistent validation semantics across devices. | High | COV-020,COV-027 | Risk inferred from migration and cross-brand context in Epic scope.