## Overview
G2-16480 UAT - Shipping Options New Provider
Epic Key | G2-16480
Epic Slug | shipping-options-new-provider
Generated Date | 2026-08-05
Epic Summary | Shipping Options - New Provider
Epic Status | Done
Created By | Cavazzuti, Matilde ¦¦ LuxExperience
Component | CA
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 35-45 minutes
Coverage Summary | 7 UI-testable stories mapped to 10 business checks and 10 coverage rows. 14 backend-only/spike/setup stories are excluded from direct business execution.
Stories In Scope | G2-17592 ¦ BE: Multiple Shipment Functionality Brand dependent ¦ Done G2-20488 ¦ BE: Implement Shipping Method Selection Endpoint (Tapir) ¦ Done G2-20492 ¦ BE: Remove default shipment logic ¦ Done G2-20496 ¦ BE: Implement a new endpoint for fetching available shipping methods (Tapir) ¦ Done G2-20657 ¦ BE: Implement Shipping Method Selection GraphQL Mutation (Hyena) ¦ Done G2-20660 ¦ BE: Implement a new query for fetching available shipping methods (Hyena) ¦ Done G2-21737 ¦ FE Spike ¦ NAP & MRP Shipping Options Display and Selection ¦ Done
Stories Excluded | G2-17594 ¦ BE: Multiple Shipment Data Model ¦ Backend-only data model work. G2-17595 ¦ BE: Multiple Shipment Logic for Order assignment ¦ Backend assignment logic not directly UI-executable. G2-17929 ¦ BE Spike ¦ Falcon integration setup ¦ Discovery/setup spike. G2-17930 ¦ BE: Falcon Proxy ¦ Integration plumbing story. G2-19116 ¦ BE: Tapir making aggregate dynamic for items search allignment ¦ Backend defect unrelated to direct business UAT path. G2-19415 ¦ BE: Mock Falcon via Mockoon ¦ Mock infrastructure ticket. G2-19416 ¦ BE: Create Falcon Client in Tapir ¦ Marked in Jira as no direct QA testcase needed. G2-19417 ¦ BE: Shipping Method provider creation ¦ Provider abstraction implementation. G2-19725 ¦ BE Spike ¦ Shipping Options Implementations Details ¦ Evaluation spike. G2-20180 ¦ BE: Create new repository for Falcon and clone the code ¦ Repository setup activity. G2-20212 ¦ BE: Fix Falcon mock config ¦ Mock service alignment ticket. G2-20477 ¦ BE: Data Model Mapping for YNAP/Tapir Mismatch (ACL) ¦ Integration mapping layer ticket. G2-20494 ¦ BE: Split OrderShipmentProcessor by brand ¦ Internal refactor ticket. G2-20721 ¦ BE: Falcon Shipping Method provider creation ¦ Backend provider implementation.
Out of Scope | Fast checkout specific variants, carrier contract-dependent signature opt-out behavior, and deep API-internal implementation verification.
Dev Evidence | Trigger summary: triggered stories=7/7; GitHub lookups executed=7 (3 successful, 4 rate-limited); Confluence lookups executed=2. Evidence source basis: GitHub MCP plus Jira description/comments/issuelinks fallback scan. Story evidence availability: 3 Available, 4 Evidence Unavailable.
Gaps Summary | GitHub secondary rate limit prevented commit evidence retrieval for 4 triggered stories (G2-20496, G2-20657, G2-20660, G2-21737). Jira fallback scan found no explicit PR/commit URLs for those stories. Several acceptance criteria are technical and require business interpretation for UI outcomes.
Token Telemetry | payload_bytes=15022; payload_chars=15022; est_tokens~3756; checklist_rows=10; matrix_rows=10; exploratory_rows=4
Output Path | uat-test-plans/G2-16480-shipping-options-new-provider.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cavazzuti, Matilde ¦¦ LuxExperience | Shipping Options Visibility | Available shipping options are shown during checkout for the active shipment | 1. Open checkout shipping step with a valid cart that has shippable items. 2. Confirm options list is displayed for each shipment context. | Shipping options are visible for the shipment context. No blocking empty-state error is shown for valid carts.
UAT-002 | Cavazzuti, Matilde ¦¦ LuxExperience | Selection and Update | Customer can choose a shipping option and persist selection | Select one method, continue, then return to shipping step and verify selected method remains. | Selection is accepted and persisted. Order summary reflects the selected method.
UAT-003 | Cavazzuti, Matilde ¦¦ LuxExperience | Default and Fallback | Default shipping option is applied when customer does not manually change it | Proceed through shipping without changing the preselected method and review checkout summary and backend-visible result. | A default method is applied and checkout can proceed. Default behavior is consistent with epic AC intent.
UAT-004 | Cavazzuti, Matilde ¦¦ LuxExperience | Split Shipment Rule | Split-shipment behavior follows expected local and remote shipment option constraints | Use a split cart scenario and verify local shipment has selectable methods while remote shipment behavior follows expected rule set. | Local shipment offers selectable methods. Remote shipment rule application is consistent with configured behavior.
UAT-005 | Cavazzuti, Matilde ¦¦ LuxExperience | Cart State Lifecycle | Porter empty-cart flow does not fail before first item is added | Create or use an empty cart, set address, then add first item and continue shipping flow. | No blocker occurs while cart has no shipment yet. Shipment-related flow initializes correctly after first item is added.
UAT-006 | Cavazzuti, Matilde ¦¦ LuxExperience | Validation and Error Handling | Invalid shipment or method inputs surface safe, user-facing errors | Exercise invalid shipmentId/method/cart combinations via UI path and verify visible feedback while checkout stays stable. | Errors are handled without breaking checkout. Messages are consistent and do not expose internal details.
UAT-007 | Cavazzuti, Matilde ¦¦ LuxExperience | Authorization | Shipping option access respects cart ownership and user context | Run guest and logged-in paths and validate that cart access from another user context is not exploitable. | Authorized user/guest flows work. Cross-user access does not expose or mutate protected cart data.
UAT-008 | Cavazzuti, Matilde ¦¦ LuxExperience | Cross-Brand Compatibility | Porter and mytheresa-compatible behaviors coexist without regression | Execute core shipping-option checks on both target storefronts and compare expected behavior deltas. | Brand-specific behavior is respected. No regression blocks the existing mytheresa-like flow.
UAT-009 | Cavazzuti, Matilde ¦¦ LuxExperience | Checkout Summary Reflection | Chosen shipping option is reflected in checkout summary consistently | Select methods in each scenario and inspect checkout summary presentation before final confirmation step. | Summary reflects selected option per shipment context. Displayed value remains consistent after navigation.
UAT-010 | Cavazzuti, Matilde ¦¦ LuxExperience | Device and Performance | Core shipping options behavior is consistent on desktop and mobile checkout | Repeat critical checks on desktop and mobile viewport for NAP and MRP acceptance storefronts. | Core flow is usable on both form factors. No visible performance blocker in loading options list.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-17592 | AC-G2-17592-FF | Brand-dependent multiple shipment toggle and transparent behavior switch | High | UAT-008 | Partial | GitHub commits found via MCP for G2-17592 in tapir and tapir-deployment | Available | Regression | Story AC is technical; business validation inferred through cross-brand behavior checks.
COV-002 | G2-20488 | AC-G2-20488-SEL | Shipment-level method selection endpoint behavior | High | UAT-002,UAT-006,UAT-007 | Partial | GitHub commit evidence found; Jira QA comment confirms EXPRESS/STANDARD and guest/logged-in tests | Available | Functional | Acceptance text references API-level tests; mapped to business-level outcomes.
COV-003 | G2-20492 | AC-G2-20492-EMPTYCART | No default shipment/method on porter empty cart with safe lifecycle | High | UAT-005,UAT-008 | Partial | GitHub commit evidence found for default shipment logic removal | Available | Regression | Detailed technical AC requires business interpretation of expected UX transitions.
COV-004 | G2-20496 | AC-G2-20496-FETCH | Retrieve available methods through new porter-oriented endpoint | High | UAT-001,UAT-004,UAT-006 | Partial | GitHub lookup attempt failed due secondary rate limit; Jira fallback scan found no explicit PR/commit URL | Evidence Unavailable | Functional | Jira comment indicates cross-user cart returns 200 empty list; potential policy ambiguity versus stricter forbidden response expectations.
COV-005 | G2-20657 | AC-G2-20657-MUT | GraphQL mutation for selecting shipment shipping method | High | UAT-002,UAT-006,UAT-007 | Partial | GitHub lookup attempt failed due secondary rate limit; Jira fallback scan found no explicit PR/commit URL | Evidence Unavailable | Functional | Mutation acceptance is API-centric; UAT maps to observable checkout effects.
COV-006 | G2-20660 | AC-G2-20660-QUERY | GraphQL query for shipment shipping methods retrieval | High | UAT-001,UAT-006,UAT-007 | Partial | GitHub lookup attempt failed due secondary rate limit; Jira fallback scan found no explicit PR/commit URL | Evidence Unavailable | Functional | Stolen cart behavior accepted as 200 empty list in Jira notes; monitor as potential authorization semantics gap.
COV-007 | G2-21737 | AC-G2-21737-FE | Display and selection UX for NAP and MRP shipping options | High | UAT-001,UAT-002,UAT-004,UAT-009 | Inferred | Confluence scenario page retrieved (ID 186978245); GitHub lookup attempt rate-limited; Jira fallback had no PR/commit URL | Evidence Unavailable | Functional | Story itself is a spike-style statement; scenario details sourced from Confluence clarification page.
COV-008 | G2-16480 | AC-EPIC-001 | Customers can see and choose shipping options based on location and timing | High | UAT-001,UAT-002,UAT-010 | Partial | Epic AC plus story-level synthesis; Confluence Shipping Options page used for context | Available | Functional | Country matrix still marked as not fully confirmed in Confluence context page.
COV-009 | G2-16480 | AC-EPIC-002 | Option cost and conditions are visible and understandable | Medium | UAT-001,UAT-009 | Inferred | Epic AC and FE scenario clarifications from Confluence | Available | Usability | Exact wording and placement may vary by design scenario and shipment type.
COV-010 | G2-16480 | AC-EPIC-003 | Default option handling when customer skips manual selection | High | UAT-003,UAT-004 | Partial | Epic AC plus backend lifecycle stories G2-20492 and G2-20496 | Available | Regression | Default behavior differs by shipment scenario and brand rules; validate scenario coverage explicitly.

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
OBS-001 | Jira Comment | G2-20496 | Cross-user cart token attempt returned 200 with empty list and was accepted as aligned behavior | Repeat with a known non-owned cart token and observe response behavior in shipping methods flow | No shipping options leakage or mutation for unauthorized cart context | Security/authorization semantics | COV-004,COV-006 | Captured from Jira QA comment thread
OBS-002 | Confluence | G2-21737 | Scenario 2 requires FE-side sorting logic for remote shipment option based on local selection | In split shipment setup, switch local shipment method and verify remote method default/rule transition | Remote shipment option follows documented rule set without manual conflict | Business rule consistency | COV-007,COV-010 | Confluence page 186978245
OBS-003 | Confluence | G2-16480 | Country matrix confirmation is pending in Shipping Options documentation | Run smoke checks across key countries used for NAP/MRP acceptance test scope | No unexpected missing options due to unresolved matrix setup | Coverage confidence | COV-008,COV-009 | Confluence page 168302384
OBS-004 | Jira Comment | G2-20488 | Local testing evidence references code-freeze constraints on acceptance deployment | Reconfirm key selection scenarios directly on acceptance environments in this UAT cycle | Observed behavior matches prior local validation results | Release confidence | COV-002,COV-005 | Jira comments mention reliance on local instance during freeze