## Overview
G2-16174 UAT - Reserve Product With No Stock
Epic Key | G2-16174
Epic Slug | res-10-reserve-product-with-no-stock
Generated Date | 2026-08-07
Epic Summary | RES-10 ¦ Reserve Product With No Stock
Epic Status | Done
Created By | Sohail, Katherine ¦¦ LuxExperience
Component | EIP
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 30-40 minutes
Coverage Summary | [Reduced V2 ~12% — 7/8 checks retained; AC coverage guardrail enforced] 1 UI-testable story mapped to 8 business checklist checks and 8 coverage rows. 5 backend/spike stories and 1 non-Story Evaluation item excluded from UI scope.
Stories In Scope | G2-16769 ¦ Story ¦ FE - Display the waitlist for a product ¦ Closed
Stories Excluded | G2-23809 ¦ Story ¦ BE - Handle where no stock is available ¦ Done ¦ Backend-only implementation story. G2-22813 ¦ Story ¦ BE - Change schema to allow multiple pre-reservation related to single reservation ¦ Done ¦ Backend-only schema story. G2-19559 ¦ Story ¦ [Spike] BE - Create Reservation Engine ¦ Closed ¦ Spike/backend exploration. G2-16774 ¦ Story ¦ BE - Handle no stock response from Racoon ¦ Closed ¦ Backend integration response handling. G2-16772 ¦ Story ¦ BE - Persist a Reservation with status Waitlist ¦ Closed ¦ Backend persistence behavior. G2-16684 ¦ Evaluation ¦ [Spike] Reserve a non-live item ¦ Done ¦ Non-Story issue type; out of scope by Story-only rule.
Out of Scope | Backend internals, data migration strategy, and non-UI technical diagnostics that are not directly observable by business users in Mochi.
Dev Evidence | No PR/commit references found for G2-16769 after GitHub MCP searches (global and org-scoped). Jira fallback scan across description/comments/issuelinks found no GitHub URLs or commit SHAs. Evidence status remains Unavailable.
Gaps Summary | AC for G2-16769 is minimal and does not define expected empty-state content, sort order, field visibility, or brand-specific variance. Confirm these with product/business during UAT execution.
Token Telemetry | payload_bytes=10148; payload_chars=10146; est_tokens~2537; checklist_rows=7; matrix_rows=8; exploratory_rows=2
Output Path | uat-test-plans-reduced30/G2-16174-res-10-reserve-product-with-no-stock.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Sohail, Katherine ¦¦ LuxExperience | Waitlist Retrieval | Waitlist panel can be opened for a specific product | In Mochi, search for a product known to have waitlisted reservations and open the product-level reservation view. | Waitlist area is reachable from the product reservation view. The selected product context remains visible while viewing waitlist data.
UAT-003 | Sohail, Katherine ¦¦ LuxExperience | Status Integrity | Displayed reservation statuses remain consistent with WAITLIST expectation | Inspect the status field for each displayed reservation in the product waitlist. | Rows shown in waitlist view use WAITLIST status naming. No conflicting non-waitlist status is mixed into the waitlist-only view.
UAT-004 | Sohail, Katherine ¦¦ LuxExperience | Product Specificity | Waitlist list is scoped to the selected product only | Switch between two products and compare the waitlist entries returned for each product. | Changing product changes the waitlist result set. Reservations from unrelated products are not displayed.
UAT-005 | Sohail, Katherine ¦¦ LuxExperience | No Data Handling | No-waitlist case is handled clearly | Open a product with no waitlisted reservations and observe the waitlist panel behavior. | System shows a clear empty-state outcome when no WAITLIST rows exist. No stale data from previous product remains visible.
UAT-006 | Sohail, Katherine ¦¦ LuxExperience | Cross-Brand Consistency | Behavior is consistent for NAP and MRP business flows | Run the waitlist display flow in acceptance.net-a-porter.com and acceptance.mrporter.com with equivalent product test data. | Both brands expose the waitlist display capability for eligible products. No brand-specific functional breakage is observed in core waitlist visibility.
UAT-007 | Sohail, Katherine ¦¦ LuxExperience | Data Freshness | Waitlist view reflects updated backend state after refresh | After backend/test-data update to waitlist rows, refresh the product view and re-open waitlist. | Updated waitlist entries are visible after refresh. Removed or changed rows do not persist incorrectly in UI.
UAT-008 | Sohail, Katherine ¦¦ LuxExperience | Access Control | Only expected business roles can view waitlist details | Test with authorized PS/CC role and with a non-authorized role in the same environment. | Authorized role can access waitlist display for a product. Unauthorized role is prevented or receives a clear access outcome.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-16769 | AC-WAITLIST-DISPLAY-CORE | Display waitlist reservations for a specific product | High | UAT-001 | Full | Jira AC explicitly states waitlist reservations must be displayed for a specific product. | Unavailable | Functional
COV-002 | G2-16769 | AC-WAITLIST-STATUS | Waitlist status semantics are represented correctly in UI | High | UAT-003 | Partial | Status semantics inferred from epic context and linked backend stories describing WAITLIST persistence. | Unavailable | Regression | Story AC does not define exact status label formatting for UI rows.
COV-003 | G2-16769 | AC-PRODUCT-SCOPING | Results are scoped to selected product | High | UAT-004 | Full | Specific product scope is stated in AC and Confluence frontend task line. | Unavailable | Functional
COV-004 | G2-16769 | AC-EMPTY-STATE | No-result behavior is handled without stale or misleading output | Medium | UAT-005 | Inferred | Not explicitly documented; added as business-critical guardrail for operational usage. | Unavailable | UX | AC does not define expected copy or behavior when no waitlist entries exist.
COV-005 | G2-16769 | AC-CROSS-BRAND | Core waitlist visibility works consistently across NAP and MRP | Medium | UAT-006 | Inferred | Epic value statement includes both NET-A-PORTER and MR PORTER business teams. | Unavailable | Regression | No explicit per-brand acceptance wording at story level.
COV-006 | G2-16769 | AC-DATA-REFRESH | Waitlist display reflects latest state after refresh | Medium | UAT-007 | Inferred | Confluence goal implies operational usage where current waitlist state must be visible. | Unavailable | Functional | Refresh/update mechanics are not specified in AC.
COV-007 | G2-16769 | AC-ROLE-ACCESS | Authorized business roles can access waitlist details | Medium | UAT-008 | Partial | Role context appears in story persona (PS/CC agent) but authorization behavior is not explicitly described. | Unavailable | Security | AC omits concrete role/permission outcomes.
COV-008 | G2-16769 | AC-DOC-ALIGNMENT | Story behavior aligns with Slice 10 frontend task definition | Low | UAT-001, UAT-004 | Full | Confluence page 'Slice 10 - Reserve product with no stock' lists frontend task to display WAITLIST reservations for a specific product. | Unavailable | Functional

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | AC Ambiguity | G2-16769 | Story AC provides only one high-level requirement without detailed display rules | Run UAT with business stakeholder to confirm expected table columns, ordering, and empty-state behavior for waitlist display. | Business confirms a single agreed behavior set that can be reused for both brands. | Medium | COV-002,COV-004,COV-005 | No additional implementation notes were present in Jira comment thread beyond 'This will work out of the box'.
EXP-002 | Evidence Gap | G2-16769 | No direct PR/commit evidence was found for the story key | Request implementation reference from engineering or confirm whether work was delivered under a different linked key before sign-off. | Either a traceable implementation reference is provided or the team accepts Jira/Confluence-only evidence for UAT closure. | Low | COV-001,COV-008 | GitHub searches for G2-16769 returned zero commits/code hits; Jira fallback link scan also returned no GitHub URLs/SHAs.