## Overview
G2-16392 UAT — Wishlist Single WL Login Features
Epic Key | G2-16392
Epic Slug | wishlist-single-wl-login-features
Generated Date | 2026-08-07
Epic Summary | Wishlist ¦ Single WL ¦ Login + Features
Epic Status | Done
Created By | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com
Component | D3
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 35-50 minutes
Coverage Summary | 9 UI-testable child stories mapped to 10 business checklist checks; 36 items excluded from business execution scope (35 non-Story issues plus 1 Story excluded by backend/migration/evaluation rule).
Stories In Scope | G2-19741 ¦ FE ¦ PDP ¦ Mini PDP Unavailable and Sold out ¦ Done G2-18775 ¦ FE ¦ Delete from WL Notification ¦ Closed G2-18774 ¦ FE ¦ Wishlist Empty State ¦ Done G2-18773 ¦ FE ¦ Wishlist Skeleton ¦ Done G2-18682 ¦ FE ¦ Delete item from WL ¦ UNDO ¦ Done G2-18655 ¦ FE ¦ Delete from WL ¦ Done G2-18186 ¦ FE ¦ WL ¦ Product remains in WL after A2C (add to WL mutation) ¦ Done G2-17808 ¦ FE Render single WL ¦ Closed G2-16808 ¦ FE ¦ WL Require Login/Registration ¦ Done
Stories Excluded | Story excluded by backend/migration/evaluation rule: G2-18797 ¦ Story ¦ Done ¦ [SPIKE] FE ¦ WL Require Login/Registration Non-Story items excluded by story-only scope: G2-21517 ¦ Task ¦ Done ¦ BE ¦ Revert Wishlist to Cart functionality changes G2-21005 ¦ Task ¦ Done ¦ FE ¦ WL ¦ update design for Empty WL page G2-20975 ¦ Bug ¦ Closed ¦ FE ¦ WL Login/Registration form - fix margins, fix modal in landscape G2-20967 ¦ Task ¦ Done ¦ FE ¦ WL ¦ AddToWishlist not showing on mobile G2-20900 ¦ Technical Story ¦ Closed ¦ BE ¦ WL ¦ access token G2-20826 ¦ Technical Story ¦ Done ¦ BE ¦ WL ¦ Return correct 'displayImages' value for product in 'xGetWishlist' query G2-20801 ¦ Technical Story ¦ Done ¦ BE ¦ WL ¦ Return correct 'color' value for product in 'xGetWishlist' query G2-20798 ¦ Technical Story ¦ Done ¦ BE ¦ WL ¦ Maintain correct ordering of Wishlist variants in 'XGetWishlist' based on the date they were added G2-20777 ¦ Bug ¦ Closed ¦ FE ¦ WL ¦ Fix product card G2-20680 ¦ Bug ¦ Closed ¦ FE ¦ Mini PDP: apply fixes according to design G2-20578 ¦ Technical Story ¦ Done ¦ FE ¦ WL ¦ Refactor menu + API integration based on recent design changes G2-20376 ¦ Task ¦ Done ¦ FE ¦ Wishlist ¦ Refactor product list container G2-20368 ¦ Technical Story ¦ Done ¦ BE ¦ WL ¦ AddToWL - Improve xMoveFromWishlistToCart endpoint to to add a product to the cart multiple times G2-20366 ¦ Bug ¦ Closed ¦ BE ¦ AddToWL XGetWishlist query works incorrectly with Tapir(v3) G2-20364 ¦ Technical Story ¦ Closed ¦ BE ¦ AddToWL - Adapt XGetWishlist query for multiple withlists G2-20358 ¦ Technical Story ¦ Done ¦ BE ¦ AddToWL - Adapt the logic to work with Porter image format G2-20244 ¦ Evaluation ¦ Done ¦ [SPIKE] BE ¦ Wishlist Default for CD Team G2-19759 ¦ Task ¦ Closed ¦ FE ¦ WL Refactor ¦ WL Margins reduced on Product Cards G2-19757 ¦ Task ¦ Closed ¦ FE ¦ WL Refactor ¦ Mini PDP buttons (remove in mobile) G2-19409 ¦ Task ¦ Done ¦ FE ¦ WL Refactor ¦ ProductCard to match design G2-18185 ¦ Technical Story ¦ Done ¦ BE ¦ Product remains in WL after A2C G2-18184 ¦ Technical Story ¦ Closed ¦ FE ¦ WL Availability G2-18101 ¦ Technical Story ¦ Done ¦ FE ¦ WL ¦ Integrate ProductSummary into the Product List component G2-18015 ¦ Technical Story ¦ Done ¦ FE ¦ Implement the Mini PDP container G2-18014 ¦ Technical Story ¦ Done ¦ FE ¦ Implement Mini PDP Data Layer and API Integration G2-17922 ¦ Technical Story ¦ Done ¦ BE ¦ HYENA ¦ Parallel WL Schema CREATE G2-17921 ¦ Technical Story ¦ Done ¦ BE ¦ TAPIR ¦ Parallel WL Schema CREATE G2-17915 ¦ Technical Story ¦ Done ¦ FE ¦ WL Navigation Bar G2-17911 ¦ Technical Story ¦ Done ¦ BE ¦ HYENA ¦ GET Customer WL Query G2-17421 ¦ Technical Story ¦ Closed ¦ FE ¦ Shared Component ¦ ProductList Container on WL G2-17420 ¦ Technical Story ¦ Done ¦ FE ¦ Shared Component ¦ ProductCard for WL G2-17411 ¦ Technical Story ¦ Done ¦ FE ¦ Implement Wishlist Data Fetching and Query Layer G2-16809 ¦ Evaluation ¦ Done ¦ [SPIKE] WL Features: Authentication and Data G2-16806 ¦ Evaluation ¦ Done ¦ [SPIKE] WL Features: Mini PDP G2-16801 ¦ Technical Story ¦ Done ¦ BE ¦ TAPIR ¦ Get Customer WL Endpoint
Out of Scope | Backend endpoint internals, API schema-level assertions, migration/platform hardening tickets, and low-level implementation diagnostics not executable as business UAT checks.
Dev Evidence | GitHub evidence available for 7/9 in-scope stories via direct Jira-key PR lookup; inherited linked-Done lineage evidence recovered for 3 additional stories; 2 stories remain without explicit PR evidence after direct lookup + linked-Done search + Jira-link fallback.
Gaps Summary | G2-18773 and G2-17808 did not yield explicit PR/commit evidence after direct GitHub key search, linked-Done lineage checks, and Jira-link fallback scans. Several stories use sparse AC placeholders ('x'/high-level bullets), so verification relies on AC intent plus linked context.
Token Telemetry | payload_bytes=15521; payload_chars=15519; est_tokens~3880; checklist_rows=10; matrix_rows=9; exploratory_rows=3
Output Path | uat-test-plans/G2-16392-wishlist-single-wl-login-features.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Authentication Gate | Guest user is forced to login/register before wishlist actions | 1. As logged-out user, attempt wishlist entry from header and add-to-wishlist from PDP. 2. Complete login with both single-WL and multi-WL accounts. | User is redirected to authentication before wishlist mutation executes. After successful login, user can continue the intended wishlist action in a valid context.
UAT-002 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Single Wishlist Rendering | Single wishlist page renders expected product content and navigation | Open wishlist for account with one wishlist and validate layout, product card details, and basic controls across desktop and mobile breakpoints. | Single wishlist view loads without layout regressions. Product card information and controls are visible and actionable.
UAT-003 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Mini PDP | Mini PDP reflects sold-out and unavailable states correctly | Open products with sold-out and unavailable variants and inspect Mini PDP CTAs and visual state treatment. | Sold-out and unavailable states show the correct CTA behavior. Visual indicators match expected state without contradictory messaging.
UAT-004 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Delete Action | Delete from wishlist removes item from visible list | From wishlist list/grid view, delete an item and confirm list refresh and item absence. | Deleted item disappears from current wishlist list. No broken card placeholders or stale counters remain.
UAT-005 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Undo Action | Undo after delete restores item state | Delete an item, trigger Undo notification, then re-check wishlist content and card state. | Undo restores the deleted item in the expected position/state. No duplicate or inconsistent card state appears after undo.
UAT-006 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Delete Notification | Delete notification appears with meaningful message and action | Delete item and verify notification copy, timing, and Undo action affordance. | User receives immediate confirmation after delete. Notification includes clear Undo action and dismisses predictably.
UAT-007 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Empty State | Wishlist empty state appears when no products remain | Clear wishlist items or use empty account to load wishlist and inspect empty-state visuals and CTA links. | Empty state is displayed instead of broken list shell. Empty state messaging and CTA allow user recovery path.
UAT-008 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Wishlist Skeleton | Skeleton/loading state is shown while wishlist data loads | Throttle network or refresh wishlist entry and observe loading transition before content render. | Skeleton state appears during data fetch. Skeleton is replaced by final content without stuck loading artifacts.
UAT-009 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | A2C Behavior | Product remains in wishlist after Add to Cart from wishlist context | Add a wishlist product to cart and revisit wishlist list and item state afterward. | Item remains in wishlist after Add to Cart action. Cart addition does not force unintended wishlist removal.
UAT-010 | Aguilar Sayaan, Nicholas ¦¦ LuxExperience.com | Cross-Breakpoint Consistency | Core wishlist flows are consistent across desktop and mobile | Repeat login-gated add/delete/undo and empty-state checks on desktop and mobile breakpoints for NAP and MRP acceptance hosts. | Critical flows work on both breakpoints without behavior regressions. Brand surfaces preserve functional parity for covered scenarios.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-16808 | AC1 | Wishlist actions require authentication and preserve post-login intent | High | UAT-001,UAT-010 | Full | Direct PR hit: #384. Jira fallback includes additional related auth PR links #284 and #286. | Available | Functional | Login flow dependency on shared account modal and responsive layout alignment can vary by brand surface.
COV-002 | G2-17808 | AC1 | Single wishlist page renders product data, controls, and interaction states | High | UAT-002,UAT-010 | Partial | No explicit PR found by Jira-key search; no linked-Done lineage or Jira GitHub URL evidence detected. | Unavailable | Functional | Ticket notes indicate AC distributed into follow-up tickets, reducing standalone traceability.
COV-003 | G2-19741 | AC1 | Mini PDP represents sold-out and unavailable states correctly | High | UAT-003,UAT-010 | Full | Direct PR hit: #293. | Available | Functional | Acceptance verification can depend on product assortment availability at test time.
COV-004 | G2-18655 | AC1 | Delete from wishlist removes selected product | High | UAT-004,UAT-006 | Full | Direct PR hit: #255. Jira comment explicitly references this PR. | Available | Functional | None.
COV-005 | G2-18682 | AC1 | Undo after deletion restores item visibility and state | High | UAT-005,UAT-006 | Full | Direct PR hit: #485; linked evidence references delete baseline #255. | Available | Functional | Undo timing behavior may vary by notification timeout.
COV-006 | G2-18775 | AC1 | Delete notification behavior aligns with delete/undo flow | Medium | UAT-006 | Partial | No direct PR by own key; inherited linked-Done evidence from #255 and #485 via clone/relates chain. | Available | UX | Ticket marked duplicate in comments; final behavior implemented across linked tickets.
COV-007 | G2-18774 | AC1 | Empty wishlist state is shown with recovery CTA | Medium | UAT-007 | Full | Direct PR hit: #233. | Available | UX | None.
COV-008 | G2-18773 | AC1 | Wishlist skeleton/loading state appears before content render | Medium | UAT-008 | Partial | No direct or inherited PR evidence found; Jira comments indicate implementation existed but no traceable PR key match. | Unavailable | UX | Evidence traceability gap between Jira completion note and GitHub key search.
COV-009 | G2-18186 | AC1 | Adding to cart from wishlist does not remove product unexpectedly | High | UAT-009 | Full | Direct PR hit: #436; linked bug-fix lineage includes #473 for related UI button-state correction. | Available | Functional | Prior bug context indicates potential regression area for button state transitions.

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
OBS-001 | Jira Comments | G2-18186 | Acceptance verification initially blocked by no products in stock; later retested successfully. | Execute A2C-from-WL checks with both in-stock and low-stock products to confirm state transitions and CTA behavior. | WL and cart interactions remain stable regardless of assortment volatility. | Medium | COV-009 | Comments reference additional bug follow-up G2-21406.
OBS-002 | Jira Links + GitHub | G2-16808 | Authentication flow touches multiple linked implementation tickets beyond the base story. | Run login-gated flow from PDP and header on both brands; verify modal layout and return path after authentication. | Login modal behavior and continuation flow are consistent for single-WL and multi-WL accounts. | High | COV-001 | Linked PR lineage includes #338, #226, #253, #418 and Jira fallback URLs #284/#286.
OBS-003 | Evidence Gap | G2-17808,G2-18773 | Two in-scope stories have completion status but no explicit PR key evidence. | Prioritize regression checks for single-WL render and skeleton transitions in acceptance across desktop/mobile. | Behavior matches AC intent despite missing direct PR traceability. | Medium | COV-002,COV-008 | No direct key PR hit and no inheritable linked-Done PR evidence found.