## Overview
G2-21511 UAT - Updated Order History in Gecco during Rollout
Epic Key | G2-21511
Epic Slug | updated-order-history-gecco-rollout
Generated Date | 2026-08-07
Epic Summary | Updated Order History in Gecco during Rollout
Epic Status | In Progress
Created By | Cobbe, Valentina ¦¦ YOOX NET A PORTER
Component | CD1
Target URLs | Porter web My Account order history (UAT), Gecco Order History repository via integrated test data
Estimated Timebox | 40-55 minutes
Coverage Summary | 6 UI-testable stories mapped to 9 business checks and 9 coverage rows. Story-only scope applied from epic children; backend-only, migration foundation, and evaluation items excluded.
Stories In Scope | G2-23873 ¦ Map Gift Messages from Signature Packaging Context ¦ New G2-23872 ¦ Integrate WCS Product Enrichment Fields (ProductName, DesignerName, ImagePath) ¦ New G2-23871 ¦ Refactor item level discount to use totalProductDiscount as Primary Source ¦ New G2-23870 ¦ Map South Korea PCCC to PersonID and AddressLine3 ¦ New G2-23868 ¦ Enforce Strict Exception Policy for Positive Discount Amounts ¦ New G2-23398 ¦ ANT ¦ Create Order Item URL image for WCS orders ¦ Done
Stories Excluded | G2-25967 ¦ Extend shipping model to support tracking event history and timestamps ¦ Story excluded as backend-only model extension. G2-22780 ¦ Sync complete order details from WCS ¦ Story excluded as migration foundation lineage item. G2-22529 ¦ Store in Gecco Order History an order placed in WCS ¦ Story excluded as migration/bootstrap scope. G2-25690 ¦ Order Source Column Module ¦ Task excluded (non-Story, backend-only). G2-24961 ¦ Add shipment information during import from Legacy porter ¦ Task excluded (non-Story, migration). G2-24960 ¦ Ant processing order history skeleton cmd ¦ Technical Story excluded (non-Story scope, backend-only). G2-24925 ¦ Order events idempotency field ¦ Task excluded (non-Story, backend-only). G2-24808 ¦ Infra for Dataplatform for sending data ¦ Task excluded (non-Story, backend infra). G2-24807 ¦ Ant processing order updates events ¦ Technical Story excluded (non-Story scope, backend-only). G2-23638 ¦ Contract Testing using pact broker ¦ Evaluation excluded. G2-23635 ¦ Agree on mapping from WCS ¦ Evaluation excluded.
Out of Scope | Infrastructure provisioning, migration bootstrap mechanics, message queue tuning, backend pod scheduling, and non-story technical tasks/evaluations outside customer-visible UAT flows.
Dev Evidence | Trigger-gated + lineage checks executed. G2-23398 has direct PR evidence from GitHub search: ant#117, ant#113, ant#109, ant-deployment#42; Jira-link fallback also contains a GitHub blob URL. Mandatory clone/relates lineage check for linked Done story G2-22780 found ant#105 (inherited implementation evidence). For G2-23873/G2-23872/G2-23871/G2-23870/G2-23868 no PR/commit URLs were found in Jira description/comments/issuelinks and direct trigger-based key search returned no hits where attempted, so evidence remains unavailable.
Gaps Summary | Most in-scope stories are New and contain implementation hints but no merged PR references, so AC is currently the only authoritative test source for those stories. G2-23398 AC remains partially vague ('check which image'), requiring exploratory confirmation of final image formatting behavior across real products.
Token Telemetry | payload_bytes=13641; payload_chars=13641; est_tokens~3411; checklist_rows=9; matrix_rows=9; exploratory_rows=3
Output Path | uat-test-plans/G2-21511-updated-order-history-gecco-rollout.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Gift Message | Signature packaging gift message is propagated to Gecco order history | 1. Place or replay a WCS order that contains UserData giftMessage at root level with signature packaging enabled. 2. Open Gecco order history details for the order and inspect gift message fields. | Gift message text is present and matches the source payload. No truncation or null substitution occurs for non-empty messages.
UAT-002 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Catalog Enrichment | Product name, designer name, and image path are populated from WCS enrichment fields | 1. Replay an order containing ProductName, DesignerName, and ImagePath values from WCS. 2. Inspect corresponding line items in Gecco order history. | Product name and designer name match WCS source values. Image path field is populated for each eligible line item.
UAT-003 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Image Rendering | Order item image URL is correctly formatted and resolves for Porter order items | Use a known Porter order item imported through ANT and inspect rendered image URL and thumbnail behavior in order history. | Image URL follows expected brand/path format. Image loads successfully without broken placeholder.
UAT-004 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Discount Mapping | Item discount uses totalProductDiscount when present and non-zero | 1. Replay an order where item UserData includes totalProductDiscount with a non-zero value. 2. Compare Gecco item discount against source field. | Displayed item discount equals totalProductDiscount from source. No secondary adjustment sum overrides the non-zero primary field.
UAT-005 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Discount Fallback | Fallback discount calculation is applied when totalProductDiscount is missing or zero | 1. Replay an order with missing or zero totalProductDiscount and valid adjustment blocks. 2. Validate resulting line-item discount in Gecco. | Discount is computed from adjustment blocks only when primary field is missing or zero. Computed value is stable and not duplicated.
UAT-006 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | KR Compliance | For KR shipping addresses, PCCC is mapped to PersonID and fills AddressLine3 when blank | 1. Replay a KR order where PCCC exists and AddressLine3 is blank at source. 2. Validate address data in Gecco order history payload/view. | PersonID contains the exact PCCC value. AddressLine3 is populated with PCCC only when originally blank.
UAT-007 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | KR Compliance | Existing non-blank AddressLine3 is preserved for KR orders while PersonID still receives PCCC | 1. Replay a KR order where AddressLine3 already has content and PCCC exists. 2. Compare source and target address fields. | AddressLine3 original value remains unchanged. PersonID is still populated with PCCC.
UAT-008 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Data Integrity | Positive discount amounts are rejected and do not create inconsistent order history records | Inject or replay an order containing a positive discount adjustment and observe processing result and persisted state. | Processing fails fast or rejects the malformed discount payload. No partially inconsistent discount record is persisted in order history.
UAT-009 | Cobbe, Valentina ¦¦ YOOX NET A PORTER | Regression | Legacy image-path behavior regression is not reintroduced after image URL changes | Open at least one historical order previously validated by business for image rendering and compare with current output after deployment. | Previously valid item images still render correctly. No regression in image host/path transformation is detected.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-23873 | AC-1 | Gift message extraction and propagation | High | UAT-001 | Full | Story AC explicitly requires extracting root giftMessage and mapping to GiftMessage in order payload. | Unavailable | Functional | None
COV-002 | G2-23872 | AC-1 | Product/designer/image enrichment mapping | High | UAT-002 | Full | AC requires replacing PartNumber placeholder with ProductName, DesignerName, and ImagePath values. | Unavailable | Data Integrity | Field names dependency on WCS noted in story context; validate real payload naming in UAT.
COV-003 | G2-23398 | AC-1 | Image URL construction for order items | High | UAT-003 | Partial | PR evidence found: https://github.com/mytheresa/ant/pull/117, https://github.com/mytheresa/ant/pull/113, https://github.com/mytheresa/ant/pull/109, https://github.com/mytheresa/ant-deployment/pull/42. Jira description includes reference blob URL in tapir repo. | Available | Functional | AC wording is brief; final expected image pattern must be asserted during UAT.
COV-004 | G2-23871 | AC-1 | Primary discount source selection | High | UAT-004 | Full | AC explicitly prioritizes totalProductDiscount when available and non-zero. | Unavailable | Data Integrity | None
COV-005 | G2-23871 | AC-2 | Discount fallback logic | Medium | UAT-005 | Full | AC requires fallback to adjustment summation only when primary field is missing or zero. | Unavailable | Functional | None
COV-006 | G2-23870 | AC-1 | KR PCCC to PersonID mapping | High | UAT-006 | Full | AC defines KR-only extraction of PCCC and mapping to PersonID plus conditional AddressLine3 overwrite when blank. | Unavailable | Compliance | None
COV-007 | G2-23870 | AC-2 | KR AddressLine3 preservation behavior | Medium | UAT-007 | Full | Conditional overwrite requirement implies preserving existing non-blank AddressLine3. | Unavailable | Regression | None
COV-008 | G2-23868 | AC-1 | Strict rejection of positive discount amounts | High | UAT-008 | Full | AC mandates exception/error when positive discount values are received and forbids absInt normalization. | Unavailable | Data Integrity | None
COV-009 | G2-23398 | Lineage-G2-22780 | Inherited image-path implementation lineage validation | Medium | UAT-009 | Inferred | Mandatory linked-Done lineage check: G2-23398 clones Done story G2-22780. GitHub key search found inherited PR evidence https://github.com/mytheresa/ant/pull/105. | Available | Regression | None

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | Trigger-AC | G2-23398 | Clarify expected final image URL format when AC is vague | Compare a sample of order item image URLs before and after rollout for Porter SKUs and confirm host/path parity with expected downstream consumers. | Image URL pattern is deterministic and consistent for all sampled items. | Incorrect URL formatting causes broken image rendering in order history UI. | COV-003,COV-009 | PR and Jira evidence exists, but AC text does not define exact URL pattern contract.
EXP-002 | Trigger-RISK | G2-23868 | Malformed positive discount payload does not leave partial persisted state | Submit a controlled malformed message with positive discount and verify no order history row is partially updated while error handling remains observable. | Payload is rejected and persistence remains unchanged. | Partial writes can corrupt customer-visible totals and trust. | COV-008 | AC requires strict exception behavior; no code-level PR reference located.
EXP-003 | Trigger-BRAND | G2-23870 | KR-only PCCC behavior does not leak into non-KR countries | Run one KR and one non-KR order through the same flow and compare PersonID/AddressLine3 behavior. | PCCC mapping applies only to KR orders. | Leakage to non-KR addresses could expose incorrect personal data fields. | COV-006,COV-007 | Country-specific AC is clear; regression-style negative test is still recommended.