## Overview
G2-16258 UAT — FE PLP Content Blocks
Epic Key | G2-16258
Epic Slug | fe-plp-content-blocks
Generated Date | 2026-08-05
Epic Summary | FE: PLP ¦ content blocks
Epic Status | Done
Created By | Kozlova, Nika ¦¦ External
Component | D1
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 35-45 minutes
Coverage Summary | [Reduced V2 ~0% — 10/10 checks retained; AC coverage guardrail enforced] 11 UI-testable stories mapped to 10 business checklist checks and 11 coverage rows. 10 linked BO/QA/hub stories/tasks were excluded as non-customer-facing capability scope.
Stories In Scope | G2-21080 ¦ Story ¦ FE: PLP ¦ Content stories ¦ Closed G2-21082 ¦ Story ¦ FE: PLP ¦ Content replacement - 2 tile ¦ Closed G2-21083 ¦ Story ¦ FE: PLP ¦ Parallax content ¦ Closed G2-21084 ¦ Story ¦ FE: PLP ¦ DLP content ¦ Closed G2-21085 ¦ Story ¦ FE: PLP ¦ Designer bio ¦ Closed G2-21087 ¦ Story ¦ FE: PLP ¦ Exit gates ¦ Closed G2-22043 ¦ Story ¦ FE: PLP ¦ Text quote ¦ Closed G2-22080 ¦ Story ¦ FE: PLP Orphan items ¦ Closed G2-23000 ¦ Story ¦ FE: Align linkText to text in Mochi content blocks ¦ Closed G2-23127 ¦ Story ¦ FE: PLP ¦ Content stories updates ¦ Closed G2-23132 ¦ Story ¦ FE: PLP ¦ Hyena ¦ Content stories update ¦ Closed
Stories Excluded | G2-21276 ¦ Story ¦ FE: PLP ¦ BO ¦ Content stories ¦ Closed ¦ BO authoring capability; not customer-facing storefront validation. G2-21278 ¦ Story ¦ FE: PLP ¦ BO ¦ PID replacement 2 tiles ¦ Closed ¦ BO authoring capability; excluded from shopper-flow execution. G2-21279 ¦ Story ¦ FE: PLP ¦ BO ¦ Text quotes ¦ Closed ¦ BO authoring capability; storefront behavior covered by FE ticket. G2-21280 ¦ Story ¦ FE: PLP ¦ BO ¦ Parallax video ¦ Closed ¦ BO setup path; customer runtime covered by FE parallax story. G2-21281 ¦ Story ¦ FE: PLP ¦ BO ¦ DLP content ¦ Closed ¦ BO setup path; storefront behavior covered by FE DLP story. G2-21282 ¦ Story ¦ FE: PLP ¦ BO ¦ Exit gates ¦ Closed ¦ BO setup path; storefront behavior covered by FE exit-gates story. G2-22075 ¦ Story ¦ FE: PLP ¦ BO ¦ Designer bio ¦ Closed ¦ BO setup path; storefront behavior covered by FE designer-bio story. G2-23119 ¦ Story ¦ FE: PLP ¦ BO ¦ Content stories updates ¦ Closed ¦ BO update path; storefront update behavior covered by FE stories. G2-21896 ¦ Task ¦ Hub ¦ Designers not visible ¦ Closed ¦ Hub/platform support task; not a PLP customer interaction check. G2-23844 ¦ Task ¦ QA ¦ PLP Content ¦ Parallax video scroll ¦ Closed ¦ QA execution task; no additional product capability.
Out of Scope | CMS back-office authoring flows, non-customer technical diagnostics, and QA operational tasks not directly visible in storefront customer journeys.
Dev Evidence | GitHub MCP commit evidence found for all 11 in-scope stories across mytheresa/atelier, mytheresa/mochi, and mytheresa/hyena. Jira comment fallback also contains a direct hyena PR URL for G2-21080.
Gaps Summary | G2-23000 has no explicit Jira AC body and relies on implementation evidence and QA note for expected outcome. G2-21085 AC text references quote placement while story title references designer bio, requiring business confirmation of intended naming/behavior semantics.
Token Telemetry | payload_bytes=15044; payload_chars=15040; est_tokens~3760; checklist_rows=10; matrix_rows=11; exploratory_rows=3
Output Path | uat-test-plans-reduced30/G2-16258-fe-plp-content-blocks.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Kozlova, Nika ¦¦ External | Content Stories Carousel | Content stories carousel works across desktop and mobile with valid navigation outcomes | 1. Open a PLP with content stories on NAP and MRP in desktop and mobile views. 2. Validate cover behavior, slide progression, and redirections from carousel interactions. | Carousel supports up to configured product items and renders consistently on desktop and mobile. Desktop title click opens linked PLP while product click opens PDP. Mobile interactions follow expected tap/autoplay behavior without broken navigation.
UAT-002 | Kozlova, Nika ¦¦ External | Grid Replacement | Two-tile replacement block obeys placement and navigation rules | 1. Locate a PLP containing the two-tile replacement content block on desktop and mobile. 2. Confirm row position and click-through behavior. | Block replaces two product tiles and does not render on the last row. Overlay/link routes to intended editorial or PLP destination. Behavior is consistent across NAP and MRP storefronts.
UAT-003 | Kozlova, Nika ¦¦ External | Parallax Experience | Parallax content transitions correctly by viewport and asset type | 1. On PLP desktop, observe parallax section through scrolling and breakpoint resizing. 2. On mobile, verify fallback behavior and muted video default when video is used. | Desktop parallax remains pinned for expected range then rejoins scroll flow. At smaller breakpoint behavior falls back to non-parallax replacement mode. Video is muted by default and content remains legible with expected opacity treatment.
UAT-004 | Kozlova, Nika ¦¦ External | DLP Hero Content | DLP content blocks render at top with expected responsive and filter behavior | 1. Open designer listing pages with configured DLP content on desktop and mobile. 2. Apply filters and verify persistence/removal behavior based on result availability. | Desktop shows two content blocks and mobile shows one where configured. Content is positioned at DLP top across supported pages. Filter outcomes follow AC expectations when result count reaches zero.
UAT-005 | Kozlova, Nika ¦¦ External | Designer Bio & Quote Blocks | Designer-bio and quote-style content blocks follow permitted placement | 1. Inspect PLPs where designer bio/text quote blocks are configured. 2. Confirm location constraints and visual integration in product grid. | Configured quote/bio content sits inside PLP grid and respects row-position restrictions. Rendering does not break surrounding product tiles. Cross-brand behavior is consistent at desktop and mobile breakpoints.
UAT-006 | Kozlova, Nika ¦¦ External | Exit Gates | Exit gates appear below pagination and navigate correctly | 1. Navigate to PLPs with exit-gate configuration and scroll below pagination. 2. Open links from exit-gate assets in both brands. | Exit gates are displayed below pagination on intended pages. Links route to expected destination content without broken paths. Image-only constraint is respected for configured assets.
UAT-007 | Kozlova, Nika ¦¦ External | Orphan Item Handling | PLP avoids orphaned final-row products when content blocks alter grid | 1. Use PLPs with content blocks and paginate/scroll to trigger data prefetch. 2. Validate row-fill behavior on desktop and mobile across at least one filtering scenario. | Final rows are completed using calculated padding items from next-page data where applicable. Behavior adapts to column count differences across breakpoints. Only last absolute page may retain orphan items when no further data exists.
UAT-008 | Kozlova, Nika ¦¦ External | Content Block Text Binding | Mochi content block text/link field alignment is preserved in storefront output | Validate a content block configured with text in CMS and confirm matching text/link rendering in PLP components that consume Mochi payload. | Rendered call-to-action text matches configured CMS text field semantics. No legacy field mismatch causes missing or incorrect link labels.
UAT-009 | Kozlova, Nika ¦¦ External | Content Stories Extended Assets | Content stories support optional middle and closing cover assets | 1. On configured PLPs, verify carousel with mandatory cover and optional middle/closing covers. 2. Confirm optionality behavior when secondary assets are absent. | Mandatory cover always renders. Optional middle and closing covers render only when provided and do not break carousel flow. Desktop and mobile behavior remains stable.
UAT-010 | Kozlova, Nika ¦¦ External | Cross-Service Propagation | New cover assets propagate from CMS source to storefront consumer services | Publish updated content stories assets and verify downstream storefront consumption path reflects new assets for both brands. | Published assets are propagated and rendered in expected consumer flow. No stale asset payload appears after publish/update cycle.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-21080 | AC-Content-Stories-Core | PLP content stories carousel interactions and redirects | High | UAT-001 | Full | Commit 9eefe98 in mytheresa/atelier; Jira comment references hyena PR #2486. | Available | Functional
COV-002 | G2-21082 | AC-Replacement-2Tile | Two-tile content replacement position and destination behavior | High | UAT-002 | Full | Commit 4d49d2c in mytheresa/atelier. | Available | Functional
COV-003 | G2-21083 | AC-Parallax-Viewport | Parallax block behavior across viewport and scroll phases | High | UAT-003 | Full | Commit 3e584ca in mytheresa/atelier. | Available | Functional
COV-004 | G2-21084 | AC-DLP-Top-Content | DLP content hero blocks placement and responsive count | High | UAT-004 | Full | Commit d69752e in mytheresa/atelier. | Available | Functional
COV-005 | G2-21085 | AC-Designer-Bio-Placement | Designer-bio content block placement semantics in PLP | Medium | UAT-005 | Partial | Commit dab625d in mytheresa/atelier. | Available | UX | Story title references designer bio while AC text references quote-last-row constraints.
COV-006 | G2-21087 | AC-Exit-Gates | Exit-gate placement below pagination and content navigation | Medium | UAT-006 | Full | Commit a0f9bf6 in mytheresa/atelier. | Available | Functional
COV-007 | G2-22043 | AC-Text-Quote-Placement | Text quote block placement inside PLP grid | Medium | UAT-005 | Full | Commit ca6cc8e in mytheresa/atelier. | Available | UX
COV-008 | G2-22080 | AC-Orphan-Item-Resolution | Row completion via dynamic padding products from subsequent result page | High | UAT-007 | Full | Commit ec4754a in mytheresa/atelier; Confluence G2-19378 design notes reviewed. | Available | Regression
COV-009 | G2-23000 | AC-LinkText-Alignment | Mochi linkText/text field alignment for content-block labels | Medium | UAT-008 | Partial | Commits 6ffd3aa and d02298f in mytheresa/mochi. | Available | Regression | No explicit acceptance criteria are present in Jira description.
COV-010 | G2-23127 | AC-Stories-Optional-Covers | Support optional middle/closing covers in content stories carousel | High | UAT-009 | Full | Commit 03e5ff0 in mytheresa/atelier. | Available | Functional
COV-011 | G2-23132 | AC-Propagation-Hyena | Propagation of additional cover assets through Hyena consumer path | High | UAT-010 | Full | Commits 0a89c2d and 7e52e5d in mytheresa/hyena. | Available | Integration

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | AC Ambiguity | G2-21085 | Designer bio story naming and AC wording use mixed quote/bio terminology. | Confirm with product/design whether designer bio and quote patterns are separate capabilities or one reused component variant. | Single agreed taxonomy for content block variants is documented and reflected in Jira AC wording. | Medium | COV-005,COV-007 | Title indicates designer bio; AC states quote placement constraints.
EXP-002 | Confluence Note | G2-22080 | Orphan-item strategy depends on dynamic viewport column calculations and next-page prefetch assumptions. | Compare desktop/mobile grid completion under layout switches and confirm no visual glitches during scroll/pagination transitions. | Row-fill behavior remains stable when breakpoints change and no duplicate/disorienting product jumps appear. | High | COV-008 | Confluence page G2-19378 discusses dynamic padding approach and trade-offs.
EXP-003 | Evidence Gap | G2-23000 | Behavior expectations rely on commit metadata because Jira story body lacks AC text. | Capture explicit business acceptance examples for text/link label mapping and verify against CMS-authored scenarios. | Documented acceptance examples remove ambiguity for future regression checks. | Medium | COV-009 | Commit messages indicate field rename from linkText to text without Jira AC detail.