## Overview
G2-16176 UAT — Site Header Set-up
Epic Key | G2-16176
Epic Slug | site-header-set-up
Generated Date | 2026-08-05
Epic Summary | NAP ¦ MRP ¦ Site Header Set-up
Epic Status | Done
Created By | Sane, Sridevi Mayuresh ¦¦ LuxExperience
Component | D2
Target URLs | https://acceptance.net-a-porter.com/en-de, https://acceptance.mrporter.com/en-de
Estimated Timebox | 35-45 minutes
Coverage Summary | [Reduced ~30% — 7/10 checks retained, lowest-priority sections dropped] 11 UI-testable stories/bugs mapped to 10 business checklist checks and 11 coverage rows. 2 QA execution tasks excluded as non-product-capability items.
Stories In Scope | G2-16829 ¦ Story ¦ Build Site Header for Guest users ¦ Closed G2-17249 ¦ Story ¦ Build Site Header for Logged-in Users (FE) ¦ Done G2-17283 ¦ Technical Story ¦ Icon Set-up ¦ Closed G2-17898 ¦ Story ¦ Build Site Header for Guest users - Part 2 (PR) ¦ Closed G2-18613 ¦ Bug ¦ Header incorrect styling ¦ Closed G2-18672 ¦ Bug ¦ Vite plugin includes MRP SVGs in NAP build ¦ Closed G2-19001 ¦ Bug ¦ Incorrect Header border ¦ Closed G2-20997 ¦ Story ¦ Remove Sticky Header On Up-scroll on PDP ¦ Done G2-22132 ¦ Bug ¦ Fix animation when logout ¦ Closed G2-22476 ¦ Bug ¦ Customer Name Clipped on Mobile ¦ Closed G2-22702 ¦ Bug ¦ Customer Name in Header Clipped on Desktop ¦ Closed
Stories Excluded | G2-20577 ¦ Task ¦ QA ¦ Header E2E testing (Logged out) ¦ Done ¦ QA execution task; no new product behavior. G2-20868 ¦ Task ¦ QA ¦ Header E2E testing (Logged in) ¦ Done ¦ QA execution task; no new product behavior.
Out of Scope | Backend implementation internals, CI pipeline behavior, and non-business technical diagnostics beyond user-observable header behavior.
Dev Evidence | GitHub MCP lookups in repo mytheresa/atelier returned direct PR evidence for 10/11 in-scope stories. G2-22702 is marked Available via Jira issuelink fallback to G2-22708 PR #824. G2-17898 remains Evidence Unavailable after GitHub + Jira fallback checks.
Gaps Summary | G2-17898 has no direct PR/commit evidence in GitHub MCP and no Jira PR URL fallback. AC language around hide/show scroll behavior overlaps with G2-20997 and should be reconfirmed per page type/device.
Token Telemetry | payload_bytes=10583; payload_chars=10579; est_tokens~2645; checklist_rows=7; matrix_rows=8; exploratory_rows=3
Output Path | uat-test-plans-reduced30/G2-16176-site-header-set-up.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Header Navigation (Guest) | Guest header shows core quick links with correct guest behavior | 1. Open NAP and MRP as guest user on desktop. 2. Verify My Account routes to sign-in and service icons (bag, wishlist, search) are visible. | My Account redirects to sign-in for guest users. Bag icon is visible without authenticated counter state. Wishlist icon is visible without authenticated alert state.
UAT-002 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Header Navigation (Logged-in) | Logged-in header routes correctly and shows account-specific states | 1. Log in on NAP and MRP. 2. Verify My Account route, wishlist alerts behavior, and bag counter behavior in both empty and non-empty bag states. | My Account links to account area for logged-in users. Bag counter state updates correctly when cart has items. Wishlist alert state is shown only when applicable.
UAT-003 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Branding & Layout | Brand header identity and border styling match expected design | Compare NAP and MRP header top area against approved UX reference for logo/brand treatment and border styling on desktop and mWeb. | Correct brand identity is shown for each site. Header border is visually correct and consistent with design references.
UAT-004 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Icon Rendering | Header icons render correctly per brand without cross-brand leakage | 1. Inspect header icons on NAP and MRP in desktop and mobile views. 2. Confirm icon style/assets belong to the active brand and load without broken states. | All required header icons render without missing or broken glyphs. NAP and MRP show the correct brand-specific icon assets.
UAT-005 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Search & Meganav | Search entry point and meganav host placeholder are present | On NAP and MRP, verify search icon/entry point is available and the header area reserves space for meganav hosting behavior. | Search entry point is visible and actionable. Meganav host area is present without layout breakage.
UAT-006 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Responsive Behavior | Header works across desktop and mobile web including hamburger menu | 1. Test NAP and MRP on desktop and mobile breakpoints. 2. Validate hamburger behavior on mobile and core header action availability at each breakpoint. | Core header actions remain accessible on all tested breakpoints. Mobile hamburger navigation appears and functions as expected.
UAT-007 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Scroll Behavior | PDP desktop no longer shows sticky header on up-scroll | 1. Open a PDP on desktop and scroll down then up. 2. Confirm the sticky header does not reappear and obscure product content. | Header does not become sticky on PDP up-scroll for desktop. PDP content remains unobstructed during scroll interactions.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-16829 | AC-Guest-Links | Guest header quick links route correctly (account, bag, wishlist) | High | UAT-001 | Full | PR #146 [G2-16829] in mytheresa/atelier. | Available | Functional
COV-002 | G2-17249 | AC-LoggedIn-Links | Logged-in header account, bag counter, wishlist alerts, and loyalty styling | High | UAT-002 | Full | PR #483 [G2-17249] in mytheresa/atelier. | Available | Functional
COV-003 | G2-17283 | AC-Icon-Ingestion | Header icon set ingestion and rendering | High | UAT-004 | Full | PR #147 [G2-17283] in mytheresa/atelier. | Available | Functional
COV-004 | G2-17898 | AC-Header-Platform-Scope | Expanded guest header scope across search, meganav host area, and platform variants | High | UAT-001, UAT-005, UAT-006 | Partial | No direct PR hit found in mytheresa/atelier for G2-17898; Jira fallback scan found no PR/commit URL. | Unavailable | Functional | AC item for hide/show on scroll is broad while PDP-specific behavior is separately implemented in G2-20997.
COV-005 | G2-18613 | Bugfix-Styling | MRP header visual styling aligns to design | Medium | UAT-003 | Full | PR #187 [G2-18613] in mytheresa/atelier. | Available | UX
COV-006 | G2-18672 | Bugfix-Brand-Assets | Vite plugin isolates brand SVG assets per build | High | UAT-004 | Full | PR #195 [G2-18672] in mytheresa/atelier. | Available | Regression
COV-007 | G2-19001 | Bugfix-Border | Header border rendering corrected across brands | Medium | UAT-003 | Full | PR #219 [G2-19001] in mytheresa/atelier. | Available | UX
COV-008 | G2-20997 | AC-PDP-Scroll | Remove sticky header on PDP up-scroll (desktop) | High | UAT-007 | Full | PRs #521 and #541 [G2-20997] in mytheresa/atelier. | Available | Functional

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | AC Ambiguity | G2-17898 | Scroll hide/show requirement wording overlaps with separate PDP sticky-header removal story | Verify header behavior matrix by page type (homepage/category/PDP) and device breakpoint with product and design stakeholders. | Behavior is consistent with latest agreed design and no unexpected sticky behavior remains on PDP desktop. | Medium | COV-004,COV-008 | G2-17898 AC includes generic hide/show statement; G2-20997 scopes PDP desktop removal.
EXP-002 | Cross-brand Risk | G2-18672 | Brand asset leakage risk across NAP/MRP builds | Run visual spot checks on critical icon set after deployment for both NAP and MRP, including guest and logged-in states. | No MRP-only assets appear on NAP and vice versa. | High | COV-003,COV-006 | Bug ticket explicitly states MRP SVGs were included in NAP build prior to fix.
EXP-003 | Browser Specific | G2-22476,G2-22702 | Header name clipping defects are platform-specific (iOS Safari and Windows Chrome) | Execute focused browser/device matrix for customer-name animation after login/logout across iOS Safari and Windows Chrome. | No clipping or baseline alignment defects appear in either environment. | High | COV-010,COV-011 | Both bug tickets include reproduction steps and screenshots tied to specific platforms.