## Overview
G2-16144 UAT — Country, Language & Location Selector
Epic Key | G2-16144
Epic Slug | country-language-location-selector
Generated Date | 2026-08-03
Epic Summary | NAP ¦ MRP ¦ Country, Language & Location Selector
Epic Status | Closed
Created By | Sane, Sridevi Mayuresh ¦¦ LuxExperience
Component | D2
Target URLs | TBD — specify target environment URL before UAT execution
Estimated Timebox | 25–35 minutes
Coverage Summary | 3 UI-testable stories (G2-17736, G2-17738, G2-19617) with 10 checklist checks covering 12 AC points across country selection, language selection, search, suggested country and footer display.
Stories In Scope | G2-17736 ¦ NAP ¦ Build & Set-up Country Language Selector & Services ¦ Closed G2-17738 ¦ MRP ¦ Build & Set-up Country Language Selector ¦ Closed G2-19617 ¦ NAP ¦ MRP ¦ Manage selected and suggested countries in Country Selector ¦ Closed
Stories Excluded | G2-17733 ¦ Locale Management, Navigations & Geolocation ¦ Technical Story ¦ Closed; team deprioritised — new tickets to be opened in future when relevant G2-18187 ¦ Investigate Currency Config on Country-Language Selector ¦ Technical Story ¦ Investigation complete; currency exposed via useCountries() hook G2-19159 ¦ Manage Flags Icon For Country Selector ¦ Technical Story ¦ Implementation approach TBD; AC not finalised at story level G2-20361 ¦ Grey divider icon bug in footer ¦ Bug ¦ Visual fix included in MRP selector delivery; no standalone AC G2-20413 ¦ Remove Hardcoded Suggested Country ¦ Bug ¦ Bug fix confirmed by QA (Sridevi, 2026-02-18); covered by G2-19617 scenarios G2-20711 ¦ QA Country & Language selector E2E testing ¦ Task ¦ Internal QA task; testing complete per Pardip Gahir (2026-02-24)
Out of Scope | Multiple language options (3+) — not supported for migration per QA confirmation Safari-specific rendering variations API-level verification of country or currency data Geo-location via Akamai infrastructure configuration Flag exceptions for HK, MO, TW — pending legal decision
Dev Evidence | G2-17736 (NAP): 2 PRs merged — #238 [G2-17736] country language selector WIP; #251 [G2-17736] Country selector [NAP] — Status: Available G2-17738 (MRP): No dedicated GitHub PR found; implementation bundled with shared NAP/MRP codebase (Jira-link fallback: caused bug G2-20361 which is fixed) — Status: Available via Jira-link fallback G2-19617 (Selected & Suggested): 2 PRs merged — #325, #332 [G2-19617] selected and suggested country; related bug fix PR #355 [G2-20413] removed cookie geo — Status: Available
Gaps Summary | G2-17738 (MRP): No dedicated GitHub PR; functional parity with NAP selector assumed based on shared codebase Flag display for HK, MO, TW: legal decision was TBC at time of writing — verify current behaviour during UAT Multiple language support (3+) explicitly descoped for migration; re-evaluate post-migration if required
Token Telemetry | payload_bytes=17835; payload_chars=17766; est_tokens~4442; checklist_rows=10; matrix_rows=12; exploratory_rows=5
Output Path | uat-test-plans/G2-16144-country-language-location-selector.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Footer Entry Point | Country selector modal opens and closes via footer trigger | 1. On any page, locate the country/flag indicator in the footer. 2. Click it to open the country selector modal. 3. Verify the modal opens. 4. Close it using the close action. | The country selector modal opens immediately on click of the footer country/flag indicator. The modal closes correctly and the footer restores to its previous state.
UAT-002 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Country Selection | Selecting a country with a single language updates the site and shows no language selector | 1. Open the country selector modal. 2. Select a country that supports only one language (e.g. 3. France). 4. Confirm the selection. 5. Verify the site switches to that country and no language selector is shown. | The site switches to the selected single-language country. No language selector is displayed for single-language countries. The footer updates to show the selected country name and applied currency.
UAT-003 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Country Selection | Selecting a country with two language options displays the language selector | 1. Open the country selector modal. 2. Select a country that supports two languages (e.g. 3. Switzerland). 4. Confirm the language selector appears. 5. Select a language and confirm. | The language selector is visible and selectable for multi-language countries. After confirming, the site reflects the chosen language. The footer updates to show the selected country name, language and currency.
UAT-004 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Language Selection | Changing language on a multi-language country updates the site language | 1. Open the country selector while already on a multi-language country. 2. Change the selected language. 3. Confirm the selection. | The site content and navigation update to reflect the newly selected language. The footer updates to show the correct language.
UAT-005 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Search | Country search by name returns correct results | 1. Open the country selector modal. 2. Type part of a country name in the search field (e.g. 3. 'Ger' for Germany). 4. Verify matching countries appear in the list. | Matching countries appear in the list as the user types. Selecting a result from the list switches the site to that country.
UAT-006 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Search | Country search by ISO code returns the correct country | 1. Open the country selector modal. 2. Type an ISO code in the search field (e.g. 3. 'DE'). 4. Verify the corresponding country (Germany) appears in the list. | The correct country matching the ISO code is returned in the search results. Selecting the result switches the site to that country.
UAT-007 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Suggested Country | Currently selected country appears as the first option in the top section of the modal | 1. Open the country selector modal. 2. Verify that the top section of the modal shows the currently active country as the first listed option. | The currently active country is shown as the first option in the top section of the country selector modal.
UAT-008 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Suggested Country | Suggested country appears in top section only when browsing from a different country | 1. Access the site from a browser location different from the currently selected country site (ensure browser location permissions are enabled). 2. Open the country selector modal. 3. Verify the top section shows the geo-located home country as a suggested option. | The suggested country (based on browser/device geo-location) appears as the second option in the top section when browsing from a different country. No suggested country is shown when the browsing country matches the selected country.
UAT-009 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Bag Rectifier | Bag rectifier appears when switching country with items in the bag | 1. Add one or more items to the bag. 2. Open the country selector modal and switch to a different country. 3. Confirm the selection. | Upon country change with items in bag, the bag rectifier modal or notification appears. The customer is informed of any item adjustments due to the country change.
UAT-010 | Sane, Sridevi Mayuresh ¦¦ LuxExperience | Footer Display | Footer displays correct country flag, country name and language/currency after selection | 1. After changing country and language, check the footer. 2. Verify the correct country flag, country name, language link (if multi-language) and applied currency are displayed. | The footer reflects the correct country flag (or no flag for HK, MO, TW if applicable), country name, language selector link and applied currency after any country change.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-17736 | AC1 | Country selector configuration — country name, flag, currency, ISO code, default language | High | UAT-002, UAT-003, UAT-010 | Full | PR #251 [G2-17736] Country selector [NAP] — merged | Available | Functional | Flag exceptions for HK, MO, TW pending legal decision — behaviour at time of UAT should be verified
COV-002 | G2-17736 | AC2 | Build FE country and language selector with placeholder copy | High | UAT-001, UAT-002, UAT-003, UAT-004 | Full | PR #238 (WIP) and #251 (final) — both merged in mytheresa/atelier | Available | Functional
COV-003 | G2-17736 | AC3 | Default language is set per country (not based on device settings) | Medium | UAT-002, UAT-003 | Full | PR #251; currency/locale data confirmed via useCountries() hook (G2-18187 technical investigation) | Available | Functional
COV-004 | G2-17736 | AC4 | Language selector shown only for multi-language countries; single-language countries show no language selector | High | UAT-002, UAT-003 | Full | Confirmed in PR #251; Confluence scenario matrix validates this for NAP desktop and mobile | Available | Functional | 3+ language countries descoped for migration — only single and dual language scenarios tested per QA (G2-20711)
COV-005 | G2-17736 | AC5 | Search country by name and by ISO code | High | UAT-005, UAT-006 | Full | PR #251 — search implemented in country selector component | Available | Functional
COV-006 | G2-17736 | AC6 | Country name in footer; clicking country or flag opens country selector | High | UAT-001, UAT-010 | Full | PR #251; Confluence scenario: 'Country flag, country name and language appear in footer' | Available | Functional
COV-007 | G2-17738 | AC1 | MRP: Country selector configuration — country name, flag, currency, ISO, default language | High | UAT-002, UAT-003, UAT-010 | Full | No dedicated GitHub PR for G2-17738; Jira-link fallback: G2-17738 caused bug G2-20361 (grey divider, fixed). Implementation shared with NAP codebase. | Available | Functional | No dedicated MRP PR identified; functional parity with NAP assumed — verify MRP explicitly during UAT
COV-008 | G2-17738 | AC4 | MRP: Language selector displayed only for multi-language countries | High | UAT-002, UAT-003 | Full | Confluence test matrix confirms scenario tested for MRP desktop and mobile | Available | Functional | 3+ language countries descoped for migration on MRP as well
COV-009 | G2-17738 | AC5-6 | MRP: Search by country name and ISO code; footer country/flag trigger | Medium | UAT-005, UAT-006, UAT-001, UAT-010 | Full | Confluence test matrix confirms search and footer scenarios for MRP | Available | Functional
COV-010 | G2-19617 | AC1-2 | New top section in country selector modal showing currently selected country as first option | High | UAT-007 | Full | PRs #325 and #332 [G2-19617] selected and suggested country — merged in mytheresa/atelier | Available | Functional
COV-011 | G2-19617 | AC3 | Suggested country shown as second option only when browsing from a different country | High | UAT-008 | Full | PRs #325, #332; bug fix PR #355 [G2-20413] removed hardcoded USA cookie geo — QA confirmed working (Sridevi, 2026-02-18) | Available | Functional | Previously hardcoded to USA — fixed in PR #355; browser geo-location permissions must be enabled for this scenario
COV-012 | G2-16144 | Epic-AC | Bag rectifier appears on country change with items in bag | Medium | UAT-009 | Partial | In epic scope ('Show bag rectifier upon country change'); no specific GitHub PR identified for bag rectifier behaviour | Available | Functional | Bag rectifier behaviour during active checkout not explicitly defined — verify with team

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | AC Gap | G2-17733 | Geo-location fallback — unsupported or failed location | Simulate a geo-location failure or set device location to an unsupported country. Access the site. Observe what country/language is applied. | The site falls back to a default locale when geo-location fails or returns an unsupported country, without crashing or showing an error to the user. | Medium | COV-007 | G2-17733 AC references: 'Given geolocation fails or returns unsupported, server redirects to default locale' — ticket closed; verify fallback is still in place
EXP-002 | AC Gap | G2-17736 / G2-17738 | Flag display for HK, MO, TW — political flag exception | Open the country selector and select or search for Hong Kong (HK), Macau (MO), or Taiwan (TW). Observe whether a flag icon is displayed. | No national flag is displayed for HK, MO, and TW per the legal decision noted in the Epic scope. A placeholder or neutral icon appears instead. | Medium — legal/compliance risk if a flag is shown | COV-001, COV-007 | Epic description: 'check any exceptions apply, e.g.: HK, MO, TW' — legal decision TBC at ticket creation
EXP-003 | Exploratory | G2-17736 / G2-17738 | Country search edge case — accented characters and partial ISO code | In the country selector search, type an accented country name (e.g. 'Österreich' for Austria) and a partial ISO (e.g. 'AT'). Observe results. | Search handles accented characters gracefully and partial ISO codes return relevant results without showing an empty state or error. | Low | COV-005, COV-009 | No specific AC for character encoding in search — exploratory edge case
EXP-004 | Exploratory | G2-19617 | Suggested country persistence — does the suggested country update if browser location changes mid-session? | Start a session with geo-location set to country A. Open the country selector and note the suggested country. Simulate a location change to country B without reloading. Re-open the selector. | Suggested country reflects the initial session geo-location value consistently, or updates gracefully, without errors. | Low | COV-011 | PR #355 resolved hardcoded suggested country; dynamic geo behaviour not fully specified in AC
EXP-005 | QA Note | G2-20711 | Multiple language options (3+) — descoped for migration; confirm no broken state | If any country in the selector is configured with 3+ languages, observe whether the selector displays correctly or breaks. | Either only 1 or 2 language options are presented to the user, or the selector handles 3+ gracefully without error. No unhandled error state. | Medium — if backend configures 3+ languages the FE may show unexpected behaviour | COV-004, COV-008 | Pardip Gahir (QA, 2026-02-24): '3+ language support not included for migration go live'