## Overview
G2-16151 UAT — PDP BE Foundation
Epic Key | G2-16151
Epic Slug | pdp-be-foundation
Generated Date | 2026-08-03
Epic Summary | PDP ¦ BE ¦ foundation
Epic Status | Closed
Created By | Kozlova, Nika ¦¦ External
Component | D3
Target URLs | TBD — specify target environment URL before UAT execution
Estimated Timebox | 15–20 minutes
Coverage Summary | 2 BE stories (G2-16715, G2-17313) with observable PDP outcomes mapped to 6 outcome-based checklist checks. All 5 evaluation/spike tickets excluded. UAT verifies end-user observable results of the BE API foundation.
Stories In Scope | G2-16715 ¦ BE ¦ PDP API ¦ Product details ¦ Closed — outcome observable: product name, brand, price on PDP G2-17313 ¦ PDP BE ¦ Tapir ¦ Generate image URLs from NAP template in Tapir ¦ Closed — outcome observable: product images on PDP
Stories Excluded | G2-16766 ¦ [SPIKE] BE ¦ PDP API ¦ Decide between URL slug or ID ¦ Evaluation ¦ Architecture decision spike — no user-facing deliverable G2-16767 ¦ [SPIKE] PDP API ¦ Validate critical path build ¦ Evaluation ¦ Internal validation spike — no user-facing deliverable G2-16838 ¦ [SPIKE] PDP API ¦ Dependency mapping ¦ Evaluation ¦ Dependency analysis spike — no user-facing deliverable G2-18479 ¦ [SPIKE] BE ¦ PDP Architecture review ¦ Evaluation ¦ Architecture review spike — outcome documented internally G2-18590 ¦ [SPIKE] BE ¦ Data for PDP details/accordions ¦ Evaluation ¦ Data investigation spike — editorial notes, size & fit, details & care data not yet exposed in API
Out of Scope | PDP accordion data (Editorial Notes, Size & Fit, Details & Care, Delivery and Returns) — under investigation in G2-18590, not yet available in API Badges, shipping restrictions, PS messaging, colour linking, recommendations, segmentation, size charts, analytics, promo — second iteration scope per epic definition Akamai Image Manager — explicitly out of scope for critical path; image URLs use imagesphere format with hardcoded width and quality until Akamai IM is formalised API-level verification (endpoint responses, schema validation) — developer concern, not business UAT
Dev Evidence | G2-17313 (Image URLs): 3 PRs merged in mytheresa/tapir — #6380 [G2-17313] add porter image host; #6423 [G2-17313] add porter image path provider brand based solution; #6479 [G2-17313] add porter image host — Status: Available G2-16715 (Product details API): No dedicated GitHub PR found; Jira comment confirms 'Already completed' — Status: Available via Jira comment fallback Note: G2-17313 has a security issue flagged in a Jira comment — flagged for Tapir team to fix
Gaps Summary | G2-16715: No GitHub PR found; implementation confirmed via Jira comment ('Already completed') but no code-level evidence trail G2-17313: Security issue flagged in Jira comment (Tapir side) — verify status of fix before UAT G2-18590: PDP accordion sections (Editorial Notes, Size & Fit, Details & Care) not yet served by API — verify which sections are populated at time of UAT Stock availability and sizes were noted as out of scope in G2-16715 AC — confirm what stock/size data is actually served at time of UAT
Token Telemetry | payload_bytes=12249; payload_chars=12175; est_tokens~3044; checklist_rows=6; matrix_rows=6; exploratory_rows=4
Output Path | uat-test-plans/G2-16151-pdp-be-foundation.xlsx

## Checklist
Check ID | Contact | Section | Check | How to Verify | Pass Criteria | Result | Notes
UAT-001 | Kozlova, Nika ¦¦ External | Product Information | PDP displays correct product name and designer/brand | 1. Navigate to a product detail page for a NAP or MRP product. 2. Verify the product name and designer/brand name are displayed correctly and match the product. | The product name is displayed and is non-empty. The designer/brand name is displayed as a single string and is correct for the product.
UAT-002 | Kozlova, Nika ¦¦ External | Product Information | PDP displays the correct product price | 1. Navigate to a product detail page. 2. Verify the price is displayed and matches the expected price for that product. | A non-empty price is displayed on the PDP. The price matches the expected value for the product.
UAT-003 | Kozlova, Nika ¦¦ External | Stock & Sizes | PDP displays product sizes with stock availability | 1. Navigate to a product detail page that has multiple sizes. 2. Verify all available sizes are listed and unavailable/out-of-stock sizes are clearly indicated. | All expected sizes for the product are displayed. Sizes that are out of stock are visually distinguished from available sizes.
UAT-004 | Kozlova, Nika ¦¦ External | Stock & Sizes | PDP correctly reflects overall stock availability status | 1. Navigate to a product that is in stock and one that is out of stock. 2. Verify the stock status is reflected correctly on each PDP. | In-stock products allow size selection and add-to-bag action. Out-of-stock products display an appropriate unavailability indicator.
UAT-005 | Kozlova, Nika ¦¦ External | Product Images | PDP displays product images without broken image states | 1. Navigate to a product detail page. 2. Verify that product images load correctly for at least two shot types (e.g. 3. front-on and back). | Product images load without broken image placeholders. At least two image shot types are displayed (e.g. 'in' and 'ou' shots).
UAT-006 | Kozlova, Nika ¦¦ External | Product Images | Product images load from the expected image host domain | 1. Inspect the image URLs on a NAP PDP and an MRP PDP. 2. Verify the domain matches the expected host (www.net-a-porter.com for NAP, www.mrporter.com for MRP). | NAP product images are served from www.net-a-porter.com. MRP product images are served from www.mrporter.com. No images are served from unexpected or placeholder domains.

## Coverage Matrix
Coverage ID | Jira Source | AC Ref | Capability | Priority | Checklist Mapping | AC Fidelity | Evidence Notes | Evidence Availability | Case Type | Inconsistencies
COV-001 | G2-16715 | AC1 | PDP API returns designer/brand name as a single, unique string | High | UAT-001 | Full | No GitHub PR found; Jira comment: 'Already completed' — implementation confirmed via Jira fallback | Available | Functional
COV-002 | G2-16715 | AC2 | PDP API returns non-empty product description | High | UAT-001 | Full | Implementation confirmed via Jira comment fallback | Available | Functional | Story AC explicitly marks stock/sizes/shipping restrictions as out of scope — confirm what is actually served at time of UAT
COV-003 | G2-16715 | Epic-AC | PDP API returns price for the product | High | UAT-002 | Partial | Price is in epic AC scope; not explicitly listed in G2-16715 story AC — inferred from epic definition | Available | Functional | Price is in epic scope but not explicitly called out in G2-16715 story AC — gap to confirm
COV-004 | G2-16715 | Epic-AC | PDP API returns sizes with availability/stock level per size | High | UAT-003, UAT-004 | Partial | Sizes and stock are in epic AC scope; G2-16715 story AC explicitly marks these as out of scope for that story | Available | Functional | G2-16715 story AC marks sizes/stock as out of scope — dependency on G2-16675 (stock availability epic, Done). Verify sizes and stock are served at time of UAT.
COV-005 | G2-17313 | AC1 | Tapir adapts image URL logic for YNAP images using imagesphere URL format | High | UAT-005, UAT-006 | Full | 3 PRs merged in mytheresa/tapir: #6380, #6423, #6479 — all closed | Available | Functional | Security issue flagged in Jira comment (Tapir side) — verify fix status before UAT. Width and quality are hardcoded until Akamai IM is implemented.
COV-006 | G2-17313 | AC2 | Image URLs use correct domain per brand (NAP vs MRP) | High | UAT-006 | Full | PR #6479 'add porter image host' and #6423 'brand based solution' directly address domain-per-brand logic | Available | Functional | Image URL format uses imagesphere pattern; will change when Akamai IM is formalised — test plan may need updating post-Akamai implementation

## Exploratory Scenarios
Observation ID | Source Type | Jira Source | Summary | How to Validate | Expected Observation | Impact | Linked Coverage IDs | Evidence Notes
EXP-001 | AC Gap | G2-17313 | Security issue flagged on Tapir image URL implementation | Check with the BE team whether the security issue flagged in G2-17313 Jira comment has been resolved. If resolved, verify no unexpected image URL exposure or path traversal is possible. | The security issue has been resolved and image URLs are served safely without exposing unintended paths or data. | High — security concern on a core product data endpoint | COV-005, COV-006 | Jira comment on G2-17313: 'security issue that needs to be fixed on Tapir side'
EXP-002 | AC Gap | G2-18590 | PDP accordion sections missing data — Editorial Notes, Size & Fit, Details & Care | Navigate to a PDP and inspect the accordion sections (Editorial Notes, Size & Fit, Details & Care, Delivery & Returns). Observe which sections are populated. | Sections with no data source yet (per G2-18590 spike) may appear empty or absent. This is expected for the current iteration. No unhandled error state should be shown. | Medium — incomplete PDP content for customers until spike outcome is implemented | COV-002 | G2-18590 is a spike to investigate data sources — outcome not yet implemented at time of this UAT
EXP-003 | Exploratory | G2-16715 | Second iteration PDP API data — badges, shipping restrictions, recommendations not yet served | Navigate to a PDP and verify that second-iteration features (badges, shipping restriction warnings, product recommendations, promo messages) are either absent or show graceful empty states. | No broken or error states where second-iteration data is expected but not yet served. Absence of these features is expected for the critical path iteration. | Low — known descope for this iteration | COV-002 | Epic scope explicitly lists these as second iteration: badges, shipping restrictions, PS messaging, colour linking, recommendations, segmentation, size charts, analytics, promo
EXP-004 | Exploratory | G2-17313 | Image URL hardcoded width and quality — verify no broken images at different viewport sizes | Open a PDP on desktop and mobile viewport sizes. Verify product images display at an acceptable quality and are not pixelated or oversized at either breakpoint. | Images display acceptably at all tested viewport sizes. Hardcoded w2000_q60 values are sufficient for current viewports. | Low — will be addressed when Akamai IM implementation is formalised | COV-005 | PR #6479 hardcodes width and quality; AC notes this will change with Akamai IM